Best Practices

for

Voluntary

Nursing Facility

Closure

Michigan Nursing Facility State Closure Team

January 2005

Best Practices for Voluntary Nursing Facility Closure

Table of Contents

Purpose of the Best Practices for Voluntary Nursing Facility Closure

The Goal of the Closure Process

Maintaining Resident Focus During the Closure Process

Flowchart of Nursing Facility Closure Process

Major Phases Involved in Resident Relocation

Notification of Closure and Initial Meetings

Information Gathering

Person-centered Discharge Planning

Visit and Selection of New Residence

Transfer of Resident and Belongings

Preparation for Resident’s Arrival at New Residence

Resident Follow-up and Closure Process Evaluation

Roles and Responsibilities

Nursing Facility

Local Closure Team

State Closure Team

Daily Checklists and Meeting Tasks

Tool Kits

Resident, Family and Guardian

Placement Worker

Nursing Facility Administrator

MDCH State Nursing Facility Closure Coordinator

Nursing Facility Director of Nursing (DON)

Scheduler

Direct Caregiver

Other Nursing Facility Staff (Activities, Business Office, Nursing Staff, All Other Staff)

Receiving Residence

Licensing Officer and Survey Monitor (LO and SM)

Medical Services Administration (MSA) Long Term Care Services Section Manager

Department of Human Services (DHS)

Local Community Mental Health Service Provider (CMH)

MIChoice Waiver Agents

Long Term Care Ombudsman (LTC Ombudsman)

Center for Independent Living (CIL)

Hospice Service Provider

Purpose Of The Best Practices for Voluntary Nursing Facility Closure

This Best Practices has been designed for use by owners, administration, staff, residents, family members, guardians, placement workers, and government representatives during resident relocation resulting from a voluntary nursing facility closure. The information presented here is intended to bring about the best possible outcomes for residents involved in a closure process by clarifying roles and responsibilities, giving examples of useful forms and procedures, and suggesting helpful resources. The first section contains a narrative explanation of the individuals and agencies involved and the closure and relocation process and can serve as a training and orientation resource.

The “tool kit” section is divided by tabs according to the role of each closure worker. These subsections are meant to be copied and distributed to the users; the sample forms, agendas, and checklists can be put directly into service or modified to suit the unique circumstances of a particular nursing facility closure.  Resource lists are placed at the back of the binder. The entire Best Practices for Voluntary Nursing Facility Closure is also available on the MDCH website at: www.michigan.gov/mdch

The Goal Of The Closure Process

To achieve the overall goal of helping residents move to a new residence while minimizing relocation stress, all parties involved must:

- Remain focused on best outcomes for residents throughout the process

- Assure that residents’ choices and preferences are considered and honored

- Acknowledge the resident’s and staff’s feelings of loss, mistrust or confusion

- Contribute to a resident focused approach necessary for a successful relocation process

- Insure safe and timely transfer of residents to new residences

- Conduct business in a professional and collaborative manner

- Support the daily routines of residents and nursing facility operations

- Create a blameless environment focusing on positive outcomes and solutions

Maintaining Resident Focus During The Closure Process

Flowchart for Nursing Facility (NF) Closure Process

Major Phases Involved in the Resident Relocation Process

- Notification of closure

- Information gathering

- Person-Centered Discharge Planning

- Visit and selection of new residence

- Physical transfer of resident and belongings

- Preparation for resident’s arrival at new residence

- Resident follow-up and closure process evaluation

Notification of Closure and Initial Meetings

As required by the Michigan Public Health Code, Act 368 of 1978, Section 21785, the nursing facility administrator must notify the State Survey Agency Licensing Officer and the MSA Long Term Care Services Section Manager as soon as possible before the anticipated date of closure, but no less than 30 days prior to closure. Written notice will be requested at the time of contact.

The Michigan Public Health Code also requires notice to be given 30 days in advance of closure to residents, family members, and residents’ representatives or guardians.  Notification 60 to 90 days in advance of an anticipated closure date is strongly encouraged to facilitate optimal timeframes for residents and families to make informed choices about relocation.

The federal notification process required by The Centers for Medicare and Medicaid Services (CMS) can be reviewed at the CMS website at:

http://www.cms.hhs.gov/medicaid/survey-cert/letters.asp

Written Notification

The written notification letter includes:

- A detailed reason for closure

- A brief closure plan including expected timeframes

- The name, address and phone number of the State LTC Ombudsman

- The name of contact person at the nursing facility for additional information

- Information about the resident and family meeting(s) for residents, families and guardians including the date, time, location and purpose

Written notice must be sent to:

- Residents, families and guardians

- MDCH, Medical Services Administration, Long Term Care Services Section Manager

- MDCH, Bureau of Health Systems, Division of Nursing Home Monitoring, Licensing Officer

Consider sending written notification to:

- State Long Term Care Ombudsman

- Nursing facility Medical Director and attending physicians

- Nursing facility contractual staff and consultants

- Nursing facility vendors

- Local hospitals

- Local community organizations

- Media

Verbal Notification

Facility administration and management staff will coordinate verbal notification to residents, families, guardians and staff, marking the first day of the closure process, as explained in Daily Checklists and Meeting Tasks.

Since the nursing facility staff know the residents best, use best judgment of how to notify residents.  Consider smaller sized groups, one-on-one meetings and/or resident/family groups at different times of the day. Develop a plan to avoid having residents hear the news by overhearing upset employees or having the resident not know the exact details for several days and worry unnecessarily.  It is best to have direct communication with the residents, supported by written notice as appropriate, explaining that additional meetings will be scheduled to discuss options and that a placement worker will be assigned to offer support to them and their families through the relocation process.

Nursing facility staff will need to be reassured of the owner’s intention to continue wages and benefits, and to assist in job placement resources.  Staff members are likely to respond with greater confidence if the notification is made directly by the administrator and/or owner.  Deliver the announcement of the closure in a supportive manner, free of blame or threat.  The full complement of nursing facility staff will be needed to complete the relocation process so assuring staff members of their continuing importance in serving residents is a key message to convey.

The nursing facility administration will assign staff to make phone calls to family members and guardians to inform them of the closure and invite them to attend a resident and family meeting.

Resident and Family Meeting

The resident and family meeting should be held by the third day of closure.  Some facilities have found it helpful to hold two meetings—one during the day and one in the evening.  The resident and family meeting is facilitated by the nursing facility administrator or owner representative.  State Agency staff will also be present and can speak about their role in the closure.  Family members often use this meeting to express their feelings about the closure, which can include anger, sadness, disappointment, fear, and loss.  We suggest that feelings be acknowledged and addressed.

It is often most helpful to allow time after the meeting for families to meet with their assigned placement worker.  It allows families to speak with a person about the process and to feel as if they are doing something to take care of their loved one.

It is not recommended that representatives from other potential residences attend the resident and family meeting.  The best option is for residents and families to visit several other residences before making a decision.

The Nursing Facility Administrator tool kit contains information on the agenda for the resident and family meeting as well as materials to prepare for the meeting.

Local Closure Team Meeting

Best practices include holding a meeting of all state agencies and contractors involved in the closure.  We suggest this meeting be held in the nursing facility, scheduled on the first day of closure, and be facilitated by the MDCH State Nursing Facility Closure Coordinator, in cooperation with the nursing facility administrator.

The meeting participants may include:

- Survey Agency staff

- Local DHS staff

- Local MIChoice Waiver agency staff

- Local CMH staff

- Local CIL representative

- Local Hospice representative

- State and local LTC Ombudsman staff

- Key Nursing Facility Staff

- Other service organizations that serve the community and nursing facility

The purposes of this meeting are to:

- Insure that all participants have correct information about what is happening

- Clarify the role of each agency in the closure

- Identify a lead person from each agency and make sure that everyone knows how to make contact with the lead

- Insure that the nursing facility administrator and staff understand the role and contact person for each agency involved in the closure

- Identify key nursing facility staff assigned to relocation tasks

- Designate the most appropriate placement worker for each resident

Information Gathering Process

Exchange of information between nursing facility staff, placement workers and the local closure team is critical to successful resident relocations.  The following information is gathered during the first few days of closure:

- Resident face sheets

- Current resident roster

- Medicaid status for all eligible residents

- Medicare benefit days remaining

- Bed availability/vacancies at other residences

- Availability of community based services

- Enforcement remedies imposed against local nursing facilities

- Ranking of local nursing facilities base on compliance history, if available

- Residents receiving CMH services

- Residents needing

a legal guardian

a Medicaid application

an OBRA screen (PASARR I or II)

- Upcoming medical procedures or appointments for residents

Person-Centered Discharge Planning Process

For the most effective discharge planning process, a resident focused approach must be used to assess the resident’s needs.  Initially, the placement worker meets with the resident and/or a family member/guardian to discuss and review the resident’s relocation preferences and quality of life concerns.

The next step in the process includes gathering information about the resident from other disciplines, including nursing, activity staff, direct caregivers, volunteers, family members, and staff from other shifts. This information includes the resident’s functional status with Activities of Daily Living (ADLs), perceived likes and dislikes, daily routines, and effective resident-specific interventions.

The placement worker determines what potential barriers exist to meeting the resident’s needs or wishes for placement and determines possible solutions.  The Person-Centered Discharge Planning tool is provided in the Placement Worker tool kit.

Visit and Selection of New Residence

Once the Person-Centered Discharge Planning tool is complete, the placement worker identifies possible relocation options based on the resident’s preferences for living arrangements, medical needs, desired geographical location, and availability of services and/or beds.  All options are considered regardless of the current level of care or resident’s medical condition.  Other agencies can be called upon to assist with a residential placement or return to the resident’s home.   On-site visits to the potential residences are the best way to insure that a good decision is made. The Comparison of On-site Visits form (included in the Resident, Family and Guardian tool kit) assists the visitor in recording information to compare multiple residences.  The completed form is a useful tool for making informed relocation decisions in cooperation with the placement worker.

Once residences of choice are identified by the resident/family/guardian, the placement worker requests that the resident’s Person-Centered Discharge Planning Form, physician’s orders and medical record face sheet are faxed to potential residences for review.  The placement worker contacts the residences to insure the information was received and reviewed and determines if the resident has been accepted for admission. In some circumstances, it has been found helpful for receiving residence staff members to visit and assess the resident personally.  The resident or guardian then makes a final decision for relocation and the placement worker notifies scheduler, who arranges transportation.

Transfer of Resident and Belongings

Preparing the resident for transfer requires support from nursing facility staff not only in the physical preparation of materials and belongings, but also with ADL assistance and emotional support for the resident.

The facility administrator will designate a scheduler who will coordinate the transfer dates and times with receiving residences.  The scheduler will limit the number of residents leaving per day and limit the number of residents to one location per day to assure adequate time for the receiving residences to properly prepare for residents’ arrivals.  Once scheduled for transfer, the placement worker notifies the resident and family/guardian of the transfer date and time.  This will allow the resident ample time to prepare for leaving.

The day before the resident is scheduled to leave, the resident’s belongings are packed with care and appropriately labeled.  The resident participates in packing and/or requests assistance from family or nursing facility staff.  Using boxes to pack belongings is a dignified touch, in contrast to using plastic bags.

The resident is bathed or showered the day before his/her scheduled transfer.  Staff considers additional hygiene assistance the day of transfer. The resident’s nails are trimmed and painted, if appropriate.  This activity allows nursing facility staff and residents an opportunity for one-on-one time.

On the day of transfer, the resident dresses in clean clothing and the resident’s hair is styled/combed.  Allow adequate time for the resident to say good-bye to other residents and nursing facility staff. An opportunity for leave-taking contributes positively to a smooth transition.  While the resident is saying his/her good-byes, belongings are loaded into the transfer vehicle.  Best Practice guidelines strongly suggest that the resident is accompanied to the new location and introduced to staff.

The scheduling and return transportation of resident escorts is determined during the daily local team meetings.

Detailed steps for the transfer process are included in the tool kits.

Preparation for Resident’s Arrival at New Residence

Staff members at the receiving residence have a significant impact on the success of the resident’s transition. By reviewing and planning ahead of time for the resident’s needs and preferences as described on the Person-Centered Discharge Planning form, the new residence is able to provide a warm, sensitive welcome tailored to the resident.

Upon arrival, the resident’s discharge transfer packet is distributed and reviewed by caregivers to insure that the resident’s needs and preferences are addressed.  For a resident with dementia, special sensitivity and care must be taken during the first days of relocation.  Consider balancing the need for resident assessment and interview with the resident’s adjustment and psychosocial needs. Best practice suggestions for residents with dementia who are being relocated are found in the tool kits.

Resident Follow-up and Closure Process Evaluation

Resident Follow-up

Placement workers make follow-up calls to new residences within 24 to 48 hours of transfer.  The Closure Coordinator will monitor to insure this activity is completed for all residents and will review the feedback for evaluation purposes.

The local ombudsmen conduct on-site visits with residents transferred to other licensed facilities in their service areas.  DHS and CMH local agency staff follow-up on residents during the next 90 days to check on their status post relocation.  Information on resident follow-up is shared with the Closure Coordinator for review and evaluation.

Closure Process Evaluation

The Closure Coordinator conducts follow-up phone calls with receiving residences to identify areas for improvement, strengths of the process, and unexpected outcomes.  Discussion meetings are scheduled with State Closure Team and Local Closure Team to identify and review strengths and areas for improvement.   The nursing facility administrator and key facility staff may be contacted by MDCH representatives for evaluation and feedback.

Once discussion with all parties is complete, suggestions for improving this Best Practices for Voluntary Nursing Facility Closure are presented to the State Closure Team for review and possible implementation.

Roles And Responsibilities

Every individual or agency involved in a resident relocation process should be familiar with his or her role and responsibilities.  Ultimately, the Michigan Department of Human Services and the Michigan Department of Community Health are responsible for insuring the safe and orderly transition of residents during any type of closure.  Toward that end, there may be several agencies and contractors on site during the closure, each with a specific and mandated role.  The nursing facility may determine a need for increased assistance from these agencies to fully implement these best practice guidelines.

Outlined in each tool kit are basic roles and responsibilities for guidance through the process of a voluntary nursing facility closure.

Nursing Facility

The nursing facility administration remains responsible for the operation of the facility, and the owner/governing body remains responsible for the oversight of the nursing facility operation. Extra steps must be taken to insure the safety and well being of residents. The nursing facility may be required to increase both monetary and manpower resources to complete additional tasks during the closure process. The nursing facility must continue its practice for insuring the confidentiality of resident information.  The nursing facility must incorporate its current evacuation plan into the closure plan in the event of an emergency or natural disaster.

Local Closure Team

Collectively, the members of the Local Closure Team are responsible for supporting the relocation process to assure a safe and orderly transfer for all residents. The team may be comprised of representatives from DHS, CMH, Ombudsman Program, MIChoice Waiver program, CIL, Hospice, and the Closure Coordinator.

State Closure Team

Under an interagency agreement, the State Closure Team is responsible for offering support to the Local Closure Team members upon request, including clarification of rules and regulations, available services, and payment methodology.  The State Closure Team is responsible for communicating initial needs for relocation services to the local level as well as addressing any issues identified by the Closure Coordinator during the relocation process.  Members of the State Closure Team include representatives from MSA, BHS, DHS, OSA, CMH (OBRA), the Closure Coordinator, and the State LTC Ombudsman.

Daily Checklists and Meeting Tasks

Prior to Day 1 – Focus on Decision to Close and Preparing Initial Notification

Day 1* – Focus on Notification and Information Gathering

Day 2 – Focus on Assessment and Person-Centered Discharge Planning Process

Day 3 – Focus on Resident and Family Meeting and Relocation Process

All Other Days – Focus on Daily Tasks to Accomplish Relocation

Last Day – Focus on Closing the Nursing Facility and Securing Records & Equipment

* Day 1 is determined by the date the nursing facility residents are notified of the closure.  In a well-planned closure, some steps from Day1 are completed prior to resident notification (i.e., notifying management staff and facility staff, scheduling the resident and family meeting, preparing notification letters for mailing, and arrival of Closure Coordinator on-site).

Daily meetings are scheduled with the Local Closure Team and the key nursing facility staff.  Meeting agendas are provided in the following pages for the first three days of closure.  On subsequent days, the daily meeting includes discussion of challenging placements, outstanding issues from previous days, a verbal update on progress by each placement worker, an update of the resident relocation roster, and an opportunity to voice concerns and ask questions.  These meetings are facilitated by the Closure Coordinator in conjunction with the Nursing Facility Administrator.

Checklist for Prior to Day 1

Focus on decision to close the nursing facility and preparing initial notification

Nursing Facility Administrator

Before the decision is made to close the nursing facility

_____ Contact nursing facility’s Licensing Officer to discuss possibility of closure

_____ Contact MSA LTC Services Manager to discuss possibility of closure

_____ Contact governing body (board of directors, owner, etc.) for final decision and closure plan development

Once the decision is made to close the nursing facility

_____  Notify nursing facility Licensing Officer by phone and in writing of closure

_____  Notify MSA LTC Services Manager by phone and in writing of closure

_____  Issue public notice of nursing facility closure in local newspaper to coordinate with resident notification (publish in paper on Day 1)

_____  Develop plan for nursing facility closure

_____  Submit closure plan and current resident roster to Closure Coordinator

Licensing Officer

_____ Offer guidance to nursing facility administrator

_____ Notify Director of the Division of Nursing Home Monitoring of nursing facility’s decision to close

_____ Review current enforcement status with Enforcement Unit in BHS/Div of Operations

_____ Schedule survey staff to monitor the nursing facility

MSA LTC Services Manager

_____ Notify MSA Administration, Reimbursement & Rate Setting and Provider Enrollment  of nursing facility closure

_____ Notify State Closure Team members of nursing facility closure

_____ Review current enforcement status with Enforcement Unit in BHS/Div of Operations

_____ Schedule arrival of Closure Coordinator at nursing facility

_____ Review financial standing of facility and identify areas of concern

_____ Coordinate notification of DCH media office with BHS

Nursing Facility Closure Coordinator

_____  Prepare supplies and materials necessary for nursing facility closure

_____  Determine availability of additional staff resources if needed

_____  Secure transportation and lodging for self and additional staff if necessary

_____  Assure adequate tool kits are prepared for initial arrival

State Closure Team Members

_____  Notify local team members of closure and require participation in relocation process

_____  Share local team members’ contact names and numbers with Closure Coordinator

Meeting Tasks for Day 1

Refer to tool kits for more details on meetings and agenda items

Checklist for Day 1

Tasks focus on notification and information gathering

Nursing Facility Administrator

_____ Determines work area for local closure team with Closure Coordinator

_____ Prepares nursing facility closure notification letter including date, time and location of resident and family meetings for immediate mailing by business office staff

_____ Prepares nursing facility closure notification letter to mail to vendors, physicians, media, state and local agencies, community groups, etc. for immediate mailing by the business office staff

Closure Coordinator

_____ Notifies local closure team members and State Closure Team Leader of resident and family meetings

_____ Requests additional placement worker resources if necessary and requests participation in Day 2 team meeting

_____ Forwards resident face sheets to local DHS office to determine Medicaid status for eligible residents

_____ Creates the resident relocation roster

_____ Prepares resident specific forms for distribution to placement workers at team meeting on Day 2

_____ Creates signs for local closure team work areas - “Closure Coordinator Work Room” and  “Local Closure Team Work Room”

_____ Reports to the State Closure Team Leader at the end of the day

Assigned Nursing Facility Staff

_____ Call families and guardians to inform them of the nursing facility closure

_____ Notify residents of closure

_____ Copy resident face sheets and resident roster and forward to Closure Coordinator

NF Business Office Staff

_____ Prepare envelopes for mailings

_____ Mail letters to families, guardians, vendors, agencies, physicians, etc.

_____ Acquire change of address cards for residents from post office

Local Department of Human Services

_____ Begins Medicaid status check on eligible residents using resident face sheets

_____ Determines bed availability/occupancy for nursing, home for aged, and adult foster care facilities

Meeting Tasks for Day 2

Refer to tool kits for more details on meetings and agenda items

Checklist for Day 2

Tasks focus on assessment and Person-Centered Discharge Planning process

Nursing Facility Administrator

_____ Complete facility assessment with Closure Coordinator

_____ Prepares agenda for Resident and Family Meetings (see sample in tool kit)

Closure Coordinator

_____ Creates materials for team meeting

_____ Serves as facilitator for team meeting

_____ Complete facility assessment with Administrator

_____ Reports to the State Closure Team Leader or designee at the end of the day

Placement Workers

_____ Begin Person-Centered Discharge Planning process

Assigned Nursing Facility Staff

_____ Continue tasks from Day 1, if not completed

_____ Reproduce materials for Resident and Family meeting

_____ Prepare Resident Transfer packets

_____ Fax resident information at placement worker request

_____ Plan for room set up and refreshments for the Resident and Family meetings

NF Business Office Staff

_____ Continue tasks from Day 1, if not completed

_____ Prepare plan to disburse Resident Trust Fund and Patient Pay balances, if necessary

Local Department of Human Services

_____ Continue tasks from Day 1, if not completed

_____ Schedule staff to participate in Resident and Family meetings

Meeting Tasks for Day 3

Refer to tool kits for more details on meetings and agenda items

Checklist for Day 3

Focus on resident and family meetings and planning for resident transfers

Nursing Facility Administrator

_____ Prepares for the resident and family meetings

_____ Serves as facilitator at meetings

_____ Sets positive tone and remains focused on residents

_____ Assigns staff to monitor residents at meeting for signs of distress

Closure Coordinator

_____ Serves as facilitator for team meeting

_____ Confirms local team members will be present at resident and family meetings

_____ Addresses any unresolved issues, questions or concerns

_____ Distributes updated Resident Relocation Roster to DHS at the end of the day

_____ Reports to the State Closure Team Leader at the end of the day

Assigned Nursing Facility Staff

_____ Continue tasks from previous days

_____ Prepare meeting room for resident and family meetings

_____ Prepare refreshments for resident and family meetings

_____ Fax resident information at placement worker request

_____ Offer assistance in packing at resident’s request

Local Closure Team Members

_____ Participate in resident and family meetings

_____ Prepare written materials to distribute at resident and family meetings

State Closure Team Members

_____ Participate in resident and family meetings

Placement Workers

_____ Continue Person-Centered Discharge Planning process

_____ Attend resident and family meetings

Residents, Families and Guardians

_____  Attend a resident and family meeting

_____ Meet with placement worker to begin Resident-centered Discharge Planning process

Meeting Tasks for All Other Days

Checklist for Last Day

Focus on closing nursing facility and securing records & equipment

Nursing Facility Administrator

_____ Contacts vendors to discuss discontinuation of services/supplies

_____ Assures all resident belongings and finances have been accounted for and transferred

_____ Assures clinical records are secure

_____ Notifies BHS in writing of location of clinical records and process to access resident information once facility is closed

_____ Addresses nursing facility licensure with Licensing Officer

_____ Discusses final cost reporting with Reimbursement and Rate Setting Section at MSA

_____ Places notice at facility entrances once facility closes to include contact information for administrator and/or owner and the date of closure

_____ Updates recorded telephone greeting to indicate contacting information for administrator and/or owner and date of closure

Closure Coordinator

_____ Confirms resident belongings and finances are disbursed

_____ Notifies the State Closure Team Leader when the last resident transfers

_____ Addresses any unresolved issues, questions or concerns

_____ Distributes final Resident Relocation Roster to local closure team members and facility administrator

_____ Obtain post closure contact information for administrator and other key facility staff

State Closure Team Leader

_____ Notifies State Closure Team that closure is completed

_____ Notifies Reimbursement and Rate Setting Section, Provider Enrollment and MSA Administration that closure is completed

Tool Kits

Designed from nursing facility closure best practice, the following tool kits will guide individuals through the nursing facility closure process.  Each kit contains roles and responsibilities, forms and checklists to complete required tasks, and resources to identify relocation options.

Resident, Family and Guardian

Resident Role and Responsibilities

Family and Guardian Role and Responsibilities

Guide for Resident/Family/Guardian During Nursing Facility Closure

Comparison of On-site Visits form

Frequently Asked Questions

Resident Rights

Resident Belongings Packing List

Agency Contact List (nursing facility specific)

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Placement Worker

Placement Worker Role and Responsibilities

Guide for Placement Worker During Nursing Facility Closure

Person-Centered Discharge Planning Form

Level of Care Placement Worksheet

Resident Placement Form

Fax Coversheet for Placement Worker (sample)

Message Form for Placement Worker (sample)

Comparison of On-site Visits form

Agency Contact List (nursing facility specific)

Resident Relocation Roster (sample)

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Nursing Facility Administrator

Nursing Facility Administrator Role and Responsibilities

Guide for Administrator During Nursing Facility Closure

NF Administrator Tasks for Nursing Facility Operations

Suggested Media Approaches

Suggested Security Approaches

Notification of Nursing Facility Closure

Verbal Notification to State Agencies

Written Notification by Facility

Notification Letter for Residents/Families (sample)

Initial Meeting with Management Staff

Initial Meetings with Staff

Initial Notification Meetings with Residents

Initial Notification and Meetings with Family/Guardians

Resident & Family Meeting Agenda (sample)

Information for Nursing Facility to Gather for Local Closure Team

Agency List for Access to Nursing Homes (distributed by MDCH – BHS)

Equipment and Supply List for Closure

Resident Belongings Delivery Form

Agency Contact List (nursing facility specific)

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Closure Coordinator

Closure Coordinator Role and Responsibilities

Guide for Closure Coordinator During Relocation

Closure Coordinator Tasks

Nursing Facility Needs Assessment Checklist

Agenda for Local Closure Team Meeting

Nursing Facility Resource Phone Roster (sample)

Resident Relocation Tracking Form (sample)

Local Closure Team Roster *

Nursing Facility Staff Roster*

Receiving Residence Roster*

Task/Team Assignments*

Facility Follow-up Post Closure

Resident Relocation Log (sample)

Agency Contact List (nursing facility specific)

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

* reproduce as poster size to hang in local closure team work room

Nursing Facility Director of Nursing

NF Director of Nursing Role and Responsibilities

Guide for Director of Nursing During Nursing Facility Closure

Person-Centered Discharge Planning Form

Transfer Packet Label

Agency Contact List (nursing facility specific)

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Scheduler

Scheduler Role and Responsibilities

Guide for Scheduler During Nursing Facility Closure

Checklist for Scheduling Transfer

Resident Placement Form (sample)

Resident Belongings Packing List (sample)

Packing Labels (sample)

Resident Relocation Roster (sample)

Agency Contact List (nursing facility specific)

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Direct Care Worker

Direct Care Worker Role and Responsibilities

Guide for Direct Care Worker During Nursing Facility Closure

Checklist for Preparing Resident for Transfer

Resident Belongings Packing List (sample)

Agency Contact List (nursing facility specific)

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Other Nursing Facility Staff (Activities, Business Office, Nursing Staff, All Other Staff)

Other Nursing Facility Staff Role and Responsibilities

Guide for Other Staff During Nursing Facility Closure

Checklist for Preparing Resident for Transfer

Person-Centered Discharge Planning form

Resident Belongings Packing List (sample)

Agency Contact List (nursing facility specific)

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Receiving Residence

Receiving Residence Role and Responsibilities

Receiving Residence Guide During Nursing Facility Closure

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Licensing Office and Survey Monitor

Licensing Office and Survey Monitor Role and Responsibilities

Licensing Office and Survey Monitor Guide During Nursing Facility Closure

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

MSA Long Term Care Services State Administrative Manager

MSA LTC Services Manager Role and Responsibilities

MSA LTC Services Manager Guide During NF Closure

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Local Department of Human Services

DHS Role and Responsibilities

DHS Guide During Nursing Facility Closure

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Local Community Mental Health Service Provider

Local CMHSP Role and Responsibilities

Local CMHSP Guide During Nursing Facility Closure

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

MIChoice Waiver Agents

Local MIChoice Waiver Agents Role and Responsibilities

Local MIChoice Waiver Agents Guide During Nursing Facility Closure

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Long Term Care Ombudsman (State and Local)

LTC Ombudsman Role and Responsibilities

LTC Ombudsman Guide During Nursing Facility Closure

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Center for Independent Living (CIL)

Center for Independent Living Role and Responsibilities

Center for Independent Living Guide During Nursing Facility Closure

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Hospice Service Provider

Hospice Service Provider Role and Responsibilities

Hospice Service Provider Guide During Nursing Facility Closure

Overview of Relocation Options

Flowchart of Nursing Facility Closure Process

Long Term Care Acronym List

Website Links and Other Resources

Resident Role and Responsibilities

The resident is the most important individual in the relocation process.  The resident’s role includes the options to:

- indicate preferences for new residence

- have a voice in the decision-making process

- attend informational meetings to learn about the reasons for the nursing facility closure and to get information about relocation options and assistance available

- participate in the Person–Centered Discharge Planning process, as able

- work with the assigned placement worker to determine the most feasible level of care placement

- participate in on-site visits to potential residences, as able

- inventory and pack personal belongings, as able

- participate in the admission and care planning process at the new residence

Family and Guardian Role and Responsibilities

If the resident is independent in decision-making, family members can offer support and guidance to the resident in the decision making process.  If the resident is unable to voice his or her preferences for relocation, active participation by family members and guardians is necessary for successful placement.

The role of family representatives and/or legal guardian include:

- attending the resident and family meeting to obtain information about the reasons for the nursing facility closure, options available for relocation and assistance available from local agencies

- communicating resident’s needs and preferences to the placement worker by actively participating in the discharge planning process

- visiting potential residences to discuss the resident’s needs and determine if the residence would be an appropriate selection

- indicating level of care and residence preference when the resident is not able

- consider visiting more often during the relocation process to support the resident emotionally

- assisting the resident when feasible to visit potential residences and help with making a final choice

- completing the admission process at the new residence prior to relocation, if applicable

Guide for Resident/Family/Guardian During NF Closure

The relocation process is often an emotional and difficult task for resident, families and guardians. These materials have been developed to assist and guide you through this process.  You will receive support from your assigned placement worker and from representatives from various agencies.  It is important for you to participate in the Person-Centered Discharge Planning process to determine the most appropriate relocation options and to visit several potential residences, if possible.  Be sure to use the Comparison of On-site Visits Form during your visits.  At any time in the process, discuss concerns with and direct questions to your assigned placement worker.  He/she can be a valuable resource and support to you.

Placement worker name

Placement worker phone number

Notes from the Resident/Family meeting

Tasks for the Resident, Family and/or Guardian During the Relocation Process

_____ Discuss needs wishes and/or concerns with assigned placement worker

_____	Participate in Person-Centered Discharge Planning process

_____ Visit potential residences

_____  Use the Comparison for On-Site Visits guide

_____ Discuss visits with placement worker to determine new residence

_____ Remove valuable or irreplaceable items (only at resident’s request/approval)

_____	Add list of items removed to the resident’s clinical record

_____	 Ask questions and voice concerns throughout the process

_____ Offer support to resident during transfer

_____ Complete the admission process at the new location within 24 hours of transfer

Comparison of On-site Visits

This guide can assist you in recording information and making informed decisions with your placement worker for relocation.  Carry it with you when visiting. It will help you to compare multiple locations.  Listed below are some areas you may want to be aware of during your visits as well as some questions you may want to ask. Not all questions are applicable to each type of relocation setting and the list is not all-inclusive.

Name of Residence 	                Contact Person		Phone Number 	Date of Visit

A ______________________       ___________________   ______________	_________

B ______________________       ___________________   ______________	_________

C ______________________       ___________________   ______________	_________

|  | Residence A Yes/No | Residence B Yes/No | Residence C Yes/No |
| --- | --- | --- | --- |
| Is the general atmosphere warm, pleasant & cheerful? |  |  |  |
| Do staff show genuine interest in and affection for residents? |  |  |  |
| Do residents look well cared for and generally content? |  |  |  |
| Is the residence clean and orderly? |  |  |  |
| Is the residence free of unpleasant odors? |  |  |  |
| Does the residence offer designated smoking areas? |  |  |  |
| Are call lights answered within a reasonable time frame? |  |  |  |
| Does the food look appetizing with adequate serving sizes? |  |  |  |
| Do residents who need help in eating receive assistance? |  |  |  |
| Does the residence offer activities that you would enjoy? |  |  |  |
| Are activities offered for residents who are relatively inactive, confined to their rooms or cognitively impaired? |  |  |  |
| Do residents have an opportunity to attend religious services and talk with their clergymen, both in and outside the home? |  |  |  |
| Is fresh drinking water within reach of the resident? |  |  |  |
| Do staff knock before entering a resident’s room? |  |  |  |
| Is there a lounge where residents can chat, read, play games, watch television or just relax away from their rooms? |  |  |  |
| Does the residence have an outdoor area where residents can get fresh air and sunshine and do residents use this area freely? |  |  |  |
| Did the residence’s representative ask about your (or your family member’s) specific needs and preferences? |  |  |  |
| Would you be satisfied living here? |  |  |  |
| Do you have adequate information about this residence to make a decision? |  |  |  |

Frequently Asked Questions

1.   How will I be supported in making the decision for a new residence?

A placement worker will be assigned to every resident to assist in the relocation process including identification of potential residences.  You are encouraged to visit and tour potential residences to determine which one best meets your needs and preferences.  The Ombudsman can coordinate support group meetings to allow you the opportunity to talk with other residents and families about your concerns and questions.

2.  How much time should I take to make a decision on a new residence?

To insure you have the most options, it is best to start the process right away by meeting with your assigned placement worker.  Vacancies can fill quickly, so it is best to not delay visiting potential residences to begin the selection process.

3. What is the best way to determine if a new residence is appropriate?

First, discuss your needs and preferences with your placement worker and identify potential residences.  It is best to visit a potential residence to determine if it is appropriate and can meet your needs.  The Comparison for On-site Visits form is an effective tool to guide you through your visit and to record information for comparing multiple residences.

4.  How will residents transfer to the new residence?

The responsibility for transportation varies depending on the type of residence the resident is transferring to and the payment source for care and services.  If the resident is Medicaid eligible and transferring to another nursing facility, the closing nursing facility scheduler will coordinate the transportation.  The resident will either transfer by ambulance (only when medically necessary) or the receiving nursing facility will make arrangements and payment for appropriate transportation.

For relocation to lesser level of care settings like home for aged, adult foster care, or a home, and for non-Medicaid eligible residents, the facility will work with resident, family and the receiving residence to determine the best mode of transportation.

5.  Who pays for the transportation to another nursing facility for a resident with Medicaid?

The family of a Medicaid eligible resident is not responsible for paying for transportation from one nursing home to another in the event of a nursing facility closure. If an ambulance is required, the closing nursing facility will bill the appropriate insurance for the transfer.   For non-ambulance transfers, the receiving nursing facility is responsible for paying for the transportation for Medicaid eligible residents.

6. How will the medical record be shared with the new residence?

The closing nursing facility will prepare a transfer packet for every resident, regardless of his/her level of care preference. The packet contains information from each section of the clinical record as well as a person-centered discharge plan.  Portions of this packet are faxed to the new residence in advance so medications and treatments can be arranged for the resident before he/she arrives. The entire packet is transferred with the resident.

7.  What is the Person-Centered Discharge Planning process?

It is the process of the resident sharing his/her preferences and wishes for relocation and making an informed choice about his/her new residence.  The resident can request assistance from family, friends, staff, and the ombudsman as well as support from any local closure team member during this process.

Discharge planning begins by the resident participating in an interview to share preferences and wishes with a placement worker. The resident then makes on-site visits or representatives from potential residences visit the resident at the closing nursing facility.  Working with the placement worker, the resident makes the final decision on his/her new residence and is involved in preparing for the transfer. The resident’s wishes and preferences remain the focus at all times.

8. How will personal belongings be prepared for transfer?

The facility administration will assign a team of staff to assist the residents in labeling, inventorying and packing belongings for transfer.  The resident and/or family are encouraged to participate in the packing process, but it is not required and the staff can be asked to complete this task.  If the family prefers to pack the belongings and transport them, the placement worker should be notified so supplies can be made available.  Residents may want family members to remove irreplaceable or valuable items to assure their safety during transportation.  Please notify the staff of any items removed from the nursing facility for inventory purposes.

9. How do Medicaid payments go to the new setting?

Medicaid follows the resident from one nursing facility to another.  In certain levels of care, the DHS Adult Service Workers will notify DHS Eligibility Services Workers to assure eligibility and access to Medicaid benefits are not interrupted.  Specific questions should be discussed with the placement worker.

10.  What happens to the resident mail that is delivered to the closing nursing facility?

Change of address cards will be completed for each resident once a new residence is selected.  Facility staff will forward any resident mail that arrives after the resident is relocated.

11. When will the resident trust fund monies be available?

The closing nursing facility will continue to provide resident access to the trust fund account.  When a resident is scheduled to leave the nursing facility, a current accounting of the trust fund and any remaining balance will be disbursed in an appropriate and timely manner.

12.  The facility is the resident’s representative payee on his/her Social Security check.  How is this changed when the resident moves?

If the new residence will become the new representative payee, the new residence must call the local Social Security office to make the change.  If a family or friend will become the new representative payee, they must take the resident’s ID to the local Social Security office to make application.   If the check arrives at the closing nursing facility, it will be returned to the Social Security office for proper routing.

13. Can a resident be readmitted to the closing nursing facility?

Readmissions for residents on a hospital stay or therapeutic leave require a case-by-case review to determine if the readmission is in the best interest of the resident.  The closing nursing facility should not admit new residents during the closure process.

Nursing Facility Resident Rights

As a resident of a nursing home, you have all the same rights and protections of all United States citizens. Nursing home residents also have certain rights and protections under the law. The nursing home must provide you with a written description of your legal rights.

Freedom from Discrimination

Nursing homes do not have to accept all applicants, but they must comply with Civil Rights laws that do not allow discrimination based on race, color, national origin, disability, age, or religion under certain conditions. If you believe you have been discriminated against, call the Department of Health and Human Services, Office of Civil Rights at 1-800-368-1019. TTY users should call 1-800-587-7697.

Respect

You have the right to be treated with dignity and respect. As long as it fits your care plan, you have the right to make your own schedule, including when you go to bed, rise in the morning, and eat your meals. You have the right to choose the activities you want to go to.

Freedom from Abuse and Neglect

You have the right to be free from verbal, sexual, physical, and mental abuse, and involuntary seclusion by anyone. This includes, but is not limited to nursing home staff, other residents, consultants, volunteers, staff from other agencies, family members or legal guardians, friends, or other individuals. If you feel you have been abused or neglected (your needs not met), report this to the nursing home, your family, your local Long-Term Care Ombudsman, or State Survey Agency. It may be appropriate to report the incident of abuse to local law enforcement or the Medicaid Fraud Control Unit (their telephone number should be posted in the nursing home).

Freedom from Restraints

Physical restraints are any manual method or physical or mechanical device, material, or equipment attached to or near your body so that you can't remove the restraint easily. They prevent freedom of movement or normal access to one's own body. A chemical restraint is a drug used to limit freedom of movement and is not needed to treat your medical symptoms.

It is against the law for a nursing home to use physical or chemical restraints, unless it is necessary to treat your medical symptoms. Restraints may not be used to punish nor for the convenience of the nursing home staff. You have the right to refuse restraint use except if you are at risk of harming yourself or others.

Money

You have the right to manage your own money or to choose someone you trust to do this for you. If you ask the nursing home to manage your personal funds, you must sign a written statement that allows the nursing home to do this for you. However, the nursing home must allow you access to your bank accounts, cash, and other financial records. The nursing home must protect your funds from any loss by buying a bond or providing other similar protections.

Information on Services and Fees

You must be informed in writing about services and fees before you move into the nursing home. The nursing home cannot require a minimum entrance fee as a condition of admission.

Privacy, Property, and Living Arrangements

You have the right to privacy, and to keep and use your personal belongings and property as long as they don't interfere with the rights, health, or safety of others. Nursing home staff should never open your mail unless you allow it. You have the right to use a telephone and talk privately. The nursing home must protect your property from theft. This may include a safe in the facility or cabinets with locked doors in resident rooms. If you and your spouse live in the same nursing home, you are entitled to share a room (if you both agree to do so).

Medical Care

You have the right to be informed about your medical condition, medications, and to see your own doctor. You also have the right to refuse medications and treatments (but this could be harmful to your health). You have the right to take part in developing your care plan. You have the right to look at your medical records and reports when you ask.

Visitors

You have the right to spend private time with visitors at any reasonable hour. The nursing home must permit your family to visit you at any time, as long as you wish to see them. You don't have to see any visitor you don't wish to see. Any person who gives you help with your health or legal services may see you at any reasonable time. This includes your doctor, representative from the health department, and your Long-Term Care Ombudsman, among others.

Social Services

The nursing home must provide you with any needed social services, including counseling, help solving problems with other residents, help in contacting legal and financial professionals, and discharge planning.

Leaving the Nursing Home

Living in a nursing home is your choice. You can choose to move to another place. However, the nursing home may have a policy that requires you to tell them before you plan to leave. If you don't, you may have to pay them an extra fee. If you are going to another nursing home, make sure that there is a bed available for you.

If your health allows and your doctor agrees, you can spend time away from the nursing home visiting friends or family during the day or overnight. Talk to the nursing home staff a few days ahead of time if you want to do this so medication and care instructions can be prepared.

Caution: If your nursing home care is covered by certain health insurance, you may not be able to leave for visits without losing your coverage.

Complaints

You have the right to make a complaint to the staff of the nursing home, or any other person, without fear of punishment. The nursing home must resolve the issue promptly.

Protection Against Unfair Transfer or Discharge

You cannot be sent to another nursing home, or made to leave the nursing home unless:

• It is necessary for the welfare, health, or safety of you or others,

• Your health has declined to the point that the nursing home can not meet your care needs,

• Your health has improved to the point that nursing home care is no longer necessary,

• The nursing home has not been paid for services you received, or

• The nursing home closes.

Except in emergencies, nursing homes must give a 30-day written notice of their plan to discharge or transfer you. You have the right to appeal a transfer to another facility.

A nursing home cannot make you leave if you are waiting to get Medicaid. The nursing home should work with other state agencies to get payment if a family member or other individual is holding your money.

Your Family and Friends

Family members and legal guardians may meet with the families of other residents and may participate in family councils.

By law, nursing homes must develop a plan of care (care plan) for each resident. You have the right to take part in this process, and family members can help with your care plan with your permission. If your relative is your legal guardian, he or she has the right to look at all medical records about you and has the right to make important decisions on your behalf.

Family and friends can help make sure you get good quality care. They can visit and get to know the staff and the nursing home's rules.

Taken from Guide to Choosing a Nursing Home, Publication No. CMS – 02174

Resident Belongings Packing List

Resident Name  	            Room number

New Residence  						Transfer

Date		Time

Belts								Skirt

Bible								Slippers

Blouse								Slip

Boots								Socks

Books / Magazine						Suit

Bra								Suspenders

Coat / Jacket							Sweater

Denture: Upper / Lower					Sweat Pants

Dress								Sweat Shirt

Eye Glasses							Ted Hose

Eye Glass Case						TV /remote taped to TV		Hat / Cap							Undershirt

Nightgown							Underwear

Pajamas							Vest

Pants / Slacks							Walker / Cane

Personal Chair (recliner / Geri)				Wall Decoration

Personal Papers						Wallet

Purse								Wheelchair

Quilt / Comforter

Radio								Bag of Personal Items ***

Robe

Shaver (Electric)

Shirt

Shoes

Shorts

*** Could include perfume, make up, hair accessories, brush, comb, cards, photos, pencils, pens, address books, jewelry, etc.

Nursing facility staff should confirm no personal resident belongings are locked in the front office, nurses’ station, nursing facility storage areas, or medication carts.

Suggestions for Supporting the Resident During Transfer

Once the resident is scheduled and prepared for relocation, the resident will need additional support during the transfer to the new residence.  The resident’s medical and psychosocial status will be considered to determine the most appropriate mode of transportation.  Family members and staff will be encouraged to escort the resident to his/her new residence.  The following steps should be considered during resident transfer.

- Check if resident is prepared to go before the vehicle arrives (belongings packed, changed into clean clothes, last minute primping, etc)

- Inform the resident when the vehicle arrives

- Load the resident’s personal belongings into the vehicle

- Allow the resident ample time to say good-bye to other residents and staff

- Adjust the vehicle’s temperature for the resident (air conditioning or heat)

- Escort the resident at the resident’s pace to the transfer vehicle

- Comfort the resident:

Talk calmly with the resident

Use physical contact to calm the resident

Offer reassurance to the resident about the move

Go at the resident’s pace – don’t rush the resident

Indicate the location of the resident’s belongings (in the vehicle, family has them, etc)

Reduce the noise within in the vehicle – consider comforting music

- If using a wheelchair lift

Show the resident how it works

Explain to the resident what to expect (noise, movement, etc)

Offer to ride on the lift with the resident, if acceptable to the driver

- When entering a bus or passenger van, point out the railings and steps to the resident

- If multiple residents are transferring on the same vehicle, consider staying on the bus with the residents while others are boarding

- Once at the new residence, assist the resident into the building

- Stay with the resident while his/her belongings are being unloaded

- Offer to assist the resident in setting up his/her room

Agency Contact List

(This sample list is for Ingham County.  A facility specific list will be created for each closure event.  Specific contact names are added once the team members are identified.)

Michigan Department of Community Health

Medical Services Administration (Medicaid)

Long term Care Services Section

Mary Gear, Manager						517 335-5827

Salli Pung, Nursing Facility Closure Coordinator		Contact at nursing facility

Reimbursement and Rate Setting Section

John Donaldson, Manager						517 335-5363

Bureau of Health Systems

Division of Nursing Home Monitoring

Cora Urquhart, Licensing Officer					517 334-8421

Tom Gorney, Survey Monitor					517 334-8427

Ombudsman

Sarah Slocum, State Long Term Care Ombudsman		866-458-9393

Kristina Schmidgall, Local Ombudsman

Central Michigan Citizens for Better Care Office		800 292-7852

4700 Ardmore Ave, #102-A, Okemos, MI 48805		517 347-7398

Family Independence Agency

Ingham County Office						517 887-9400

5303 S. Cedar Street, Lansing, MI 48911			517 887-9500 (fax)

Area Agency on Aging

Tri-County Office on Aging 					800 405-9141

5303 South Cedar Street, Lansing, MI 48911-3800		517 887-1440

Community Mental Health

Clinton-Eaton-Ingham CMH Services Program			517 346-8200

812 East Jolly Rd, Suite 215-A, Lansing, MI 48910

Michelle Townsend, MSW, OBRA Coordinator			517 346-8439

Center for Independent Living

Capital Area Center for Independent Living			517 241-0393

Ellen Weaver, Executive Director

Closing Nursing Facility

Administrator

Director of Nursing

Lead Placement Worker

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Placement Worker Role and Responsibilities

The nursing facility social worker usually has significant contact with residents, family members and guardians and is in the best position to use this knowledge of the resident and family to serve as the lead placement worker.

As the lead placement worker, the nursing facility social worker has the responsibility to:

- identify special needs of residents that must be considered during placement and convey this information to other placement workers

- identify residents who may be  appropriate for a lesser level of care

- recommend that the placement team include other qualified clinical staff or allied professionals from CMH , DHS, CIL, AAA, MI Choice Waiver program, Hospice, sister facilities or corporate staff

- assist in arranging for residents and family members to visit potential new residences

- provide emotional support and personal contact to residents and families throughout the relocation process

Placement Worker Guide During NF Closure

The placement worker guides and supports the resident and family through the relocation process.  Sharing your experience and expertise during the relocation process will assure the resident makes an informed decision when selecting a new residence.  Necessary steps for relocation are included in this tool kit.  For residents returning home or moving in with family, many of these steps are not applicable.

_____  Complete Resident Interview section of the Person-Centered Discharge Planning form

_____  Review remaining sections of the Person-Centered Discharge Planning form completed by nursing facility staff

Staff Insight Into Resident’s Quality of Life

Behavioral/Emotional (when applicable)

Screen for Independent Living (when applicable)

Functional Assessment

_____  Identify potential residences based on discharge plan and bed availability/vacancies

_____  Identify potential barriers and solutions (use Level of Care Placement Worksheet)

_____  Schedule on-site visits for resident and family/guardian

_____  Discuss visits with resident and family/guardian to rank preferences

_____  Submit completed fax coversheet forms to be faxed with resident information to potential new residences

_____  Follow-up with potential residences to determine if fax was received and reviewed

_____  Identify which residences have accepted the resident

_____  Contact the resident/family/guardian to make the final placement decision

_____  Discuss best transfer time and mode with resident

_____  Determine if the resident wants help in packing belongings

_____  Notify scheduler (submit Resident Placement form to scheduler) of acceptance & transfer time/mode recommendations and request for help with packing

_____  Once scheduled (scheduler returns of Resident Placement form and Relocation Information Card) notify resident and family/guardian of transfer date and time

_____  Give resident the Relocation Information Card with the name, address, phone number and contact person for the new residence with the transfer date and time

Person-Centered Discharge Planning Form

Resident Name  						Room Number

Placement Worker 						Resident Gender:         Male   or    Female

Does Resident Smoke?  Yes  or   No

RESIDENT INTERVIEW (conducted by placement worker)

What type of setting would you like to live in? (return home, live with family, AFC, HFA, NF, etc)

What would be important to you in this new environment? (safety, freedom, visitors, privacy, etc)

What preferences do you have for your living arrangements? (preferred furniture, organized vs lived-in)

What makes you happy?

What do you enjoy doing?

What would you like to do that you don’t do now?

How do you like your day to go?  Describe your typical day

What specific preferences do you have for care delivery? (bath vs shower, meals/day, caregiver gender)

What is your lifestyle like? (morning vs night person, introvert vs extrovert, alone vs group activities)

Resident Name  						Room Number

RESIDENT INTERVIEW continued

What is your ethnic/cultural background?

Are cultural activities   □  Very important	  □ Somewhat important	□  Not important at all

Needs/Preferences

What is your past or current religious affiliation(s) or denominations?

Spiritual or religious activities are    □ Very important    □ Somewhat important    □ Not important at all

Needs/Preferences

Support System (family, friends, neighbors, religious or community members, staff)

Important Events (anniversaries, births, deaths)

Nicknames

Hobbies

Skills

Schooling (level completed, where)

Occupation (company, how long, retired)

Veteran (war time, branch of service)

Community Organizations

Family (spouse, children, grandchildren)

Pets

Special residents or staff

How would you like to be welcomed at your new residence? (flowers, special meal, visitors, be left

alone, announcement, attend activities, etc)

Person-Centered Discharge Planning Form

Resident Name  						Room Number

STAFF INSIGHT INTO RESIDENT’S QUALITY OF LIFE (completed by nursing facility staff)

What is the resident’s preferred daily routine? (waking time, social interactions, nighttime activity, etc)

What is comforting to the resident? (type of music, certain activities, food items, possessions, etc)

Does the resident have favorite special foods or treats? (supplied by family/staff, ethnic, etc.)

What environment supports are available for the resident? (likes to sit by the window, prefers room door shut, sleeps with the lights on, likes to sit near the nurses station, etc)

Person completing this section 						Date

Person-Centered Discharge Planning Form

Resident Name  						Room Number

RESIDENTS WITH BEHAVIORAL OR EMOTIONAL DIFFICULTIES

(completed by nursing facility staff)

PSYCHOSOCIAL TRIGGERS

What emotions or situations trigger the resident? (Stressors, excitement, sadness, depression, outbursts)

Specific times or days it occurs?

Effective Interventions?

Person completing this section 						Date

Person-Centered Discharge Planning Form

Resident Name  						Room Number

SCREEN FOR RESIDENTS REQUESTING PLACEMENT

IN AN INDEPENDENT OR RESIDENTIAL SETTING

(completed by nursing facility staff)

Bathing			□ Independent		□ Partial Assistance		□ Total Assistance

Hygiene			□ Independent		□ Partial Assistance		□ Total Assistance

Dressing			□ Independent		□ Partial Assistance		□ Total Assistance

Telephone Use		□ Independent		□ Partial Assistance		□ Total Assistance

Shopping			□ Independent		□ Partial Assistance		□ Total Assistance

Food Prep			□ Independent		□ Partial Assistance		□ Total Assistance

Housekeeping		□ Independent		□ Partial Assistance		□ Total Assistance

Laundry			□ Independent		□ Partial Assistance		□ Total Assistance

Transportation		□ Independent		□ Partial Assistance		□ Total Assistance

Finances			□ Independent		□ Partial Assistance		□ Total Assistance

Mobility			□ Independent		□ Partial Assistance		□ Total Assistance

Eating			□ Independent		□ Partial Assistance		□ Total Assistance

Continence			□ Independent		□ Partial Assistance		□ Total Assistance

Comments:

Person completing this section 						Date

Person-Centered Discharge Planning Form

Resident Name  						Room Number

FUNCTIONAL ASSESSMENT (completed by facility Nursing staff)

Check if applicable

- Dependent for feeding

- Incontinence   	Bowel _____      	Bladder _____

- Dependent for bathing

- Dependent for dressing

- Tube feeding

- Elopement Risk    Explain

- IV Therapy

- Infection: Acute	    or   Chronic  			Type

- Needs Oxygen

- Pressure Ulcer(s) Location/Stage

- Dependent Transfer      x1_____     x2_____   Mechanical Lift _____

- Wheelchair for Mobility

- Communication Aids  (interpreter, communication board, sign language, hearing aid, etc)

- Special Needs or Equipment

Upcoming appointment (doctor’s name, purpose of visit or procedure, date, time, location, phone number)

Appliance on order (type, vendor, expected delivery date, contact name, phone number)

For relocation, how can the resident safely transfer?

- By ambulance (medically necessary)

- Wheelchair van with lift

- Motorized wheelchair

- Oversized wheelchair (check if it is:   wide ____   heavy _____   high____)

- Resident does not own wheelchair – transportation must supply one for transfer

- Car (ambulatory, can self-transfer and can safely ride in seat with seatbelt)

- Car (needs assistance transferring, but can safely ride in seat with seatbelt)

Person completing this section 						Date

Level of Care Placement Worksheet

Resident Name  						Room Number

Preferred level of care setting   		NF        HFA         AFC        Housing         Home

Potential Barrier to

Preferred Residence					Solution

Medical Services (medications, physician, home health, therapy, etc)

Safety (emergency contacts, environment modifications, medication administration, guardianship, etc)

Funding Source (Medicaid application needed, utilities, rent, furniture, groceries, etc)

Support Needs (transportation, social and recreational needs, access to friends and family, equipment, etc)

Other (move with current residents, guardian has different preferences, preferred placement not available, etc)

Resident Placement Form

Resident Name  							Room Number

Guardian/Family  							 Relationship

Phone Number    							Date Contact Made

Resident Preferences

1. Residence								Phone #

## Contact Name 							Fax #

Schedule on-site visit

Date		Time		Contact name		 Notified Resident/Family

Resident Info Faxed 						Reply   		           YES    NO

Date		Time				     Date	                Time

Confirm placement with Guardian		 	                       Guardian approved    YES    NO

Date		Time

2. Residence								Phone #

## Contact Name 							Fax #

Schedule on-site visit

Date		Time		Contact name		 Notified Resident/Family

Resident Info Faxed 						Reply   		           YES    NO

Date		Time				     Date	                Time

Confirm placement with Guardian		 	                       Guardian approved    YES    NO

Date		Time

3. Residence								Phone #

## Contact Name 							Fax #

Schedule on-site visit

Date		Time		Contact name		 Notified Resident/Family

Resident Info Faxed 						Reply   		           YES    NO

Date		Time				     Date	                Time

Confirm placement with Guardian		 	                       Guardian approved    YES    NO

Date		Time

Resident has requested assistance with packing    YES      NO

Resident preference for transfer time/mode

Resident Transfer Scheduled

Date		                Time			Confirmed with

Type of Transportation	Ambulance	    Receiving Residence Vehicle	Family / Volunteer

Notify of transfer date and time       Resident ______________    Family/Guardian ____________

Fax Coversheet for Placement Worker

Facility Name

Address, City, State  Zip

Phone        Fax

# Fax Cover Sheet

Contact Peron							Date

Location

Fax		(                 )

Phone		(                 )

We are forwarding information on the (insert closing facility name) resident indicated below for potential relocation to your residence.  Please review these materials to determine if you are able to accept the resident.  After review and consideration, please contact me at the number below with your decision.

Resident Name 		(insert resident’s name)

Placement Worker 	(insert placement worker’s name)

Phone Number to Call when responding     (insert placement worker’s onsite #)

Attachments:		Resident Face Sheet

Physician’s Orders

Person-Centered Discharge Planning form

## Confidentiality Notice

The information contained in this facsimile message is privileged and confidential and is intended only for the use of the individual or entity named above.  If the reader of this message is not the intended recipient or the employee, you are here notified that any dissemination, distribution, copying, or use of this communication is strictly prohibited.  If you have received this communication in error, please immediately notify the sender by telephone and destroy the materials.

Message Form for Placement Worker

Message for 								Agency

Name of Caller  							Phone

Resident name  							Relationship

Message:

Person taking message 						Date/Time

Comparison of On-site Visits

This guide can assist you in recording information and making informed decisions with your placement worker for relocation.  Carry it with you when visiting. It will help you to compare multiple locations.  Some things you may observe during your visit and some things you may have to ask. Not all questions are applicable to each type of relocation setting.

Name of Residence 	                Contact Person		Phone Number 	Date of Visit

A ______________________       ___________________   ______________	_________

B ______________________       ___________________   ______________	_________

C ______________________       ___________________   ______________	_________

|  | Residence A Yes/No | Residence B Yes/No | Residence C Yes/No |
| --- | --- | --- | --- |
| Is the general atmosphere warm, pleasant & cheerful? |  |  |  |
| Do staff show genuine interest in and affection for residents? |  |  |  |
| Do residents look well cared for and generally content? |  |  |  |
| Is the residence clean and orderly? |  |  |  |
| Is the residence reasonably free of unpleasant odors? |  |  |  |
| Does the residence offer designated smoking areas? |  |  |  |
| Are call lights answered within a reasonable time frame? |  |  |  |
| Does the food look appetizing with adequate serving sizes? |  |  |  |
| Do residents who need help in eating receive assistance? |  |  |  |
| Does the residence offer activities that you would enjoy? |  |  |  |
| Are activities offered for residents who are relatively inactive, confined to their rooms or cognitively impaired? |  |  |  |
| Do residents have an opportunity to attend religious services and talk with their clergymen, both in and outside the home? |  |  |  |
| Is there fresh drinking water within reach of the resident? |  |  |  |
| Do staff knock before entering a resident’s room? |  |  |  |
| Is there a lounge where residents can chat, read, play games, watch television or just relax away from their rooms? |  |  |  |
| Does the residence have an outdoor area where residents can get fresh air and sunshine and do residents use this area freely? |  |  |  |
| Did the residence’s representative ask about the your (or your family member’s) specific needs and preferences? |  |  |  |
| Would you be satisfied living here? |  |  |  |
| Do you have adequate information about this residence to make a decision? |  |  |  |

Agency Contact List

(This sample list is for Ingham County.  A facility specific list will be created for each closure event.  Specific contact names are added once the team members are identified.)

Michigan Department of Community Health

Medical Services Administration (Medicaid)

Long term Care Services Section

Mary Gear, Manager						517 335-5827

Salli Pung, Nursing Facility Closure Coordinator		Contact at nursing facility

Reimbursement and Rate Setting Section

John Donaldson, Manager						517 335-5363

Bureau of Health Systems

Division of Nursing Home Monitoring

Cora Urquhart, Licensing Officer					517 334-8421

Tom Gorney, Survey Monitor					517 334-8427

Ombudsman

Sarah Slocum, State Long Term Care Ombudsman		866-458-9393

Kristina Schmidgall, Local Ombudsman

Central Michigan Citizens for Better Care Office		800 292-7852

4700 Ardmore Ave, #102-A, Okemos, MI 48805		517 347-7398

Family Independence Agency

Ingham County Office						517 887-9400

5303 S. Cedar Street, Lansing, MI 48911			517 887-9500 (fax)

Area Agency on Aging

Tri-County Office on Aging 					800 405-9141

5303 South Cedar Street, Lansing, MI 48911-3800		517 887-1440

Community Mental Health

Clinton-Eaton-Ingham CMH Services Program			517 346-8200

812 East Jolly Rd, Suite 215-A, Lansing, MI 48910

Michelle Townsend, MSW, OBRA Coordinator			517 346-8439

Center for Independent Living

Capital Area Center for Independent Living			517 241-0393

Ellen Weaver, Executive Director

Closing Nursing Facility

Administrator

Director of Nursing

Lead Placement Worker

SAMPLE ** Nursing Facility Name – Resident Relocation Roster ** SAMPLE

Updated:  10/19/04

| Rm # | Resident’s Name | Placement Worker | Guardian/Family name and relationship | Guardian Family Phone # | Date Guardian Contacted | Name of New Residence | Scheduled Transfer | wants staff help to pack | Time Resident Left Facility | Date Completed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Last | First |  |  |  |  |  | Date | Time |  |  | MDS | Clinical Record | Follow-up call |
| 102 | Brown | Anna | J. Smith DHS | Judy Brown Daughter, DPOA | 999 555-6789 | 10/03/04 | ABC Nursing Home | 10/15 | AM 9:00 | Yes | 10:00a | 10/16/04 | 10/16/04 | 10/18/04 |
| 106 | Jackson | Robert | L. Jones CMH | Own guardian - no family contact |  | 10/02/04 |  |  |  | Yes |  |  |  |  |
| 210 | Smith | Larry | L. Jones CMH | ABC Guardian Legal guardian | 999 555-7777 | 10/3/04 | Sunny Acres AFC | 10/20 | AM10:00 | No |  |  |  |  |
| 212 | Jones | Bernice | M. Frank Waiver | Harry Jones Husband, guardian | 999 555-1234 | 10/2/04 | Home with family | 10/10 | PM 2:00 | No | 1:00p | 10/10/04 | 10/11/04 | 10/12/04 |

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Nursing Facility Administrator Role and Responsibilities

The nursing facility administrator continues to serve in his or role with full authority and responsibility for resident care and services, staffing for all departments, financial stability, vendors and supplies, security, safety and function of the physical plant, facility readmission practice and media relations.

The facility administrator is responsible for:

- timely notification about the planned closure to the nursing facility’s Licensing Officer, the State Medicaid Agency, nursing facility staff, residents, families and guardians

- scheduling and conducting informational meetings about the relocation process with staff, residents, families/guardians, and the local closure team

- coordinating nursing facility staff efforts with local closure team members

- addressing resident/family concerns and assisting in resolving issues

- providing supportive leadership and guidance to residents, family members and nursing facility staff during this emotionally challenging process

Nursing Facility Administrator Guide During NF Closure

The facility administrator remains responsible for facility operations during a nursing facility closure.  The administrator will receive support and guidance from the Nursing Facility Closure Coordinator.  The administrator must continue to offer leadership and support to the facility staff for a successful closure.

_____ Notify residents, families, staff and state agencies of closure

_____ Conduct meetings

_____ Distribute written notification

_____ Maintain operations and plan for additional resources during closure

_____  Assure adequate supplies are available for resident care and relocation tasks

_____ Assign staff to serve in various roles

______ Placement workers

______ Scheduler

______  to transport residents for visits

______  to fax resident information to facilities

______  to serve as receptionist when business office is closed

______  to identify resident belongings in laundry and/or storage

______  to assist residents to transfer vehicles and load residents belongings

_____ Develop approaches for media and security

_____ Complete facility assessment with closure coordinator

_____ Facilitate resident and family meetings

_____ Assign staff to gather information for placement workers and local closure team

_____ Participate in daily meetings

_____ Support staff and residents through relocation process

_____ Limit the number of residents (2 or 3) transferring to one location on any given day

_____ Limit the total number of residents leaving the nursing facility per day to 10

_____ Place notice at facility entrances once facility closes to include contact information for administrator and/or owner and the date of closure

_____ Update recorded telephone greeting to indicate contacting information for administrator and/or owner and date of closure

Nursing Facility Administrator Tasks for Nursing Facility Operations

_____  Care & Services

Ensure staff will remain in current positions during relocation

Contract for additional staff or services if necessary

Offer emotional support to staff

Be available to answer questions or redirect as appropriate

_____  Encourage volunteers to visit more frequently

Activity Director to coordinate schedule

Focus volunteer efforts on 1:1 with residents

Ask for volunteers to visit residents at receiving facilities if possible

_____  Adequate staffing to meet increased needs of residents during relocation

Packing resident belongings

Attending to emotional needs of residents

Anticipate increased call-ins

Plan for resignations during the process

Identify scheduler for all shifts and distribute contact information

_____  Financial stability

Employee payroll and benefits

Supplies

Food service

Necessary physical plant repairs

Remuneration for misplaced or damaged resident belongings

Increased cost associated with relocation process

Visits to receiving facilities (transportation & staff time)

Packing supplies – boxes, tape & labels

Overtime for personnel

_____  Union

Notify union representative and stewards of resident relocation/closure

Request assurance of on-going support with staffing

Ask for support for employees

_____  Vendors

Assure continued supplies and services

Coordinate retrieval of rented items when the last resident departs

_____  Security

Develop plan to keep residents safe and building secure during process

Be mindful of who has keys to what areas

Review individual needs for access to restricted areas

Consider hiring security services if necessary

_____  Readmissions

Readmissions should be considered on a case-by-case basis, based on resident needs

New admissions are not allowed

_____  Resident Trust Fund & Patient Pay

Prepare current accounting of the trust fund to disburse with monies at transfer

Prorate incoming PPA and forward balances to receiving locations or guardians

Suggested Media Approaches

_____  Develop plan to respond to media

Media should not be allowed in the building to film, photograph or record residents, without permission and invitation from the guardian

Identify facility spokesperson

Educate staff on need to direct media to facility spokesperson

_____  Develop plan for staff who have to pass the media coming in or out of the building

A positive reply about resident care being good and regular routines being followed can defuse negative media and allow the staff to have a voice

Caution should be given if staff are allowed to speak to the media

_____  Do not allow media to attend the Resident and Family meeting(s)

_____  Protect resident’s rights regarding privacy

Close curtains when media present

Remove residents from view of camera

Guardian must give authorization for media contact with residents

Residents do have the right to speak to media

_____  Educate all staff of expectations

_____  Identify nursing facility emergency contact for non-business hours

Note:  Local closure team members are required to direct media inquiries to the public relations contact within their agency, with the exception of the ombudsman. Ombudsman may speak to the media regarding the relocation process and resident care.

Suggested Security Approaches

Before initiating new security approaches, consider the effectiveness of the nursing facility’s current security practice to determine if it is adequate.  These suggested approaches can be helpful if there is a significant increase in the number of visitors including local closure team members, representatives from other facilities/residences, and/or agency staff.

- Assign a staff member to remain at front entrance. Require visitors to sign-in/out upon entry and exit. Supply a log and have it returned to the business office/administrator on a daily basis.  Upon entry, all individuals should be asked the reason for their visit.  If it is not to visit a specific named resident, work at the facility, or meet with a placement worker, entrance to the facility should not be granted.  The individual should be directed to the business office or administrator.

- At no time should any media representative (i.e., TV, radio or newspaper) be allowed access to the building.  If an attempt is made, a staff member should stay with the individual at the entrance while another staff member requests assistance from the administrator or manager on duty.  The only exception to this rule is if a resident who is his/her own guardian or a guardian has invited media to the facility.  In this case, the media representative must be informed of residents’ right to privacy.  Their business on-site should be conducted in a private area with only the inviting resident.  No pictures can be taken of residents in general areas without guardian consent.

- All doors should remain secure at all times. The main entrance should be used for all entries.  Consider having vendors first check-in at the main entrance and than have staff give access to the delivery entrance.  This will assure effective monitoring of items leaving the facility.

- No one should be permitted to remove any furniture, equipment, or fixtures from the building without appropriate authorization from the administrator.  If a family is taking possession of resident belongings, an itemized list should be signed by the family and retained for the clinical record.

- Discuss expectations with staff and supply emergency contact numbers to any person assigned to security.

Verbal Notification to State Agencies

Licensing Officer – Consider notifying your Licensing Officer during the decision process

Licensing Officer phone #

Date & time notified

Notes of conversation

Recommended action steps

Medicaid - Long Term Care Services State Administrative Manager

Contact name & phone #

Date & time notified

Notes of conversation

Recommended action steps

Written Notification by Nursing Facility Administration

Include in written letter

reason for relocation/closure

expected timeframe

contact person and number for additional information

brief outline of relocation plan

Recipients

Required written notification to:

State Survey agency – Licensing Officer 		date mailed

State Medicaid agency – LTCS Section Manager	date mailed

Residents			distribute at initial meeting with resident

(include resident/family meeting date, time & location in letter)

Families/Guardians 	date mailed

(include resident/family meeting date, time & location in letter)

Recommended written notification to

Staff				distribute at initial meeting with staff

Physicians			date mailed

Vendors			date mailed

Ombudsman		date mailed

Media			date mailed

Notification Letter to Residents/Families

(Modify for staff, state agencies, vendors, etc)

Date

Dear Family Members and Residents of XXXXXX:

You are receiving this letter because you or someone you are responsible for is a resident at NAME OF FACILITY, located at ADDRESS in CITY.  This letter is to advise you that the facility has made the difficult decision to discontinue operation due to XXXXXX (be specific about reasons to close and describe interventions attempted and why closure could not be avoided).

Be assured that all residents will be given ample support and time to make decisions about relocation to a new residence.  To begin the relocation process, two resident and family meetings have been scheduled for DATE and TIME.  You are encouraged to attend one of these meetings to learn more about the decision to close the nursing facility, the relocation process, the expected timeframe, potential residences and support from an assigned placement worker.

A team of experienced professionals will be onsite at the nursing facility each day to help you review placement options and answer any questions you may have.  Over the next few weeks, you may address any questions or concerns you may have about the relocation process with any of the following resources:

- Facility administration

- Local Closure Team Members (contact the administration at the nursing facility for names of local agency resources)

- Michigan Department of Community Health, Bureau of Health Systems at 517-241-2626.

- The State Long Term Care Ombudsman at 1-866-485-9393.  The ombudsman is also an excellent resource for information about resident rights and placement options.

I hope to see you at the Resident and Family meeting.  Please feel free to contact me with any questions or concerns.

Sincerely,

NAME OF ADMINISTRATOR

Initial Meeting with NF Management Staff

_____  Schedule before residents and floor staff are notified

_____  Discuss reason for decision for closure

_____  Introduce local closure team members and their roles, if present

_____  Briefly review relocation process (Closure Coordinator)

_____  Stress the importance of staff during this process

_____  Discuss staff responsibilities

Need for continuing daily routines

Additional support needed for relocation

_____  Identify key staff to assist in the relocation process

Placement worker

Scheduler

Packing Team

Transportation for on-site visits by residents

Resident escorts during transfer

Receptionist (when business office is closed)

_____  Invite key staff to participate in local closure team meeting

_____  Explain need for staff to support residents

_____  Develop plan to notify residents in 1:1 meetings

_____  Reassure staff that payroll will be met

_____  Indicate that a request for employment assistance will be made

_____  Educate staff on media issues

_____  Encourage staff to speak directly with key personnel regarding resident issues, concerns or rumors

_____ Instruct supervisors to schedule informational meetings with administration for staff/employees not on today’s schedule.  Try to meet with these individuals at the beginning of their next scheduled shift.

_____  Answer any questions and address any concerns

Initial Meetings with Nursing Facility Staff

_____  Schedule before residents are notified

_____  Discuss reason for decision for closure

_____  Introduce local closure team members and their roles, if present

_____  Briefly review relocation process (Closure Coordinator)

_____  Stress the importance of staff during this process

_____  Discuss staff responsibilities

Need for continuing daily routines

Additional support needed for relocation

_____  Explain need for staff to support residents

_____  Reassure staff that payroll will be met

_____  Indicate that a request for employment assistance will be made

_____  Educate staff on media issues

_____  Encourage staff to speak directly with key personnel and/or placement workers regarding resident issues, concerns or rumors

_____  Answer any questions and address any concerns

Initial Notification Meetings with Residents

Consider each resident when deciding how to notify them of the closure.  Some residents may receive this information better in a 1:1 meeting, while other residents may benefit from a small group meeting where they have an opportunity to interact with other residents.  The nursing facility staff know the residents best and should use their best judgment to determine which meeting type would be most supportive and beneficial for each resident.

_____ **Schedule special resident council meeting with council president approval (Day 1)

and/or

_____ **Assign key staff for 1:1 meetings with residents

_____  Prepare a short overview (or use notification letter) of the details for staff to follow

_____  Staff should

Discuss reason for decision to close

Identify expected timeframes for relocation

Assure resident care and services will be consistent through relocation process

Indicate families/guardians will be informed

Indicate a placement worker will be assigned to assist the resident

Briefly review relocation process

Answer any questions residents may have

Record questions staff are not able to answer and bring back to daily meeting

_____  Staff should emotionally support residents through these meetings

_____  Consider how to address residents who become very upset by the news

Assign staff to increase 1:1 time with resident

Offer to contact his/her family immediately

Offer to have resident speak on phone with family or friend

Redirect resident to minimize focus on the negative

Recognize that residents may react with distress or become upset

Be considerate of feelings, but don’t feed into them

_____ ** Inform the resident of the Resident and Family meetings

Encourage resident to attend a meeting to receive more information

Offer to escort the resident to the meeting

Indicate family and guardians will be invited to the meetings

** For the Resident and Family meeting, consider if the resident will benefit from attending.  Information from the meeting can be shared in a 1:1 meeting if this approach is best for the resident.  Residents do not have to attend this meeting.

Notification and Meetings with Family/Guardians

_____  Schedule meetings for Day 3

Date

Time

Consider an afternoon & evening meeting to accommodate schedules

Location

_____  Identify nursing facility staff to contact families on Day 1 about the closure and resident and family meetings - Keep accurate records on who has been contacted

_____  Post signs at the nursing facility entrance with information about the meetings

_____  Schedule nursing facility staff to assemble the meeting room

Allow adequate room for resident wheelchairs, seating for families and exit isles

_____  Ask the dietary department staff to serve refreshments

_____  Assign nursing facility staff to escort residents to the meeting room

_____  Identify in advance, residents who may have a difficult time at the meeting and develop a plan on addressing their needs

_____  Identify speakers for the meeting

Nursing Facility Administrator

MDCH representative(s)

DHS representatives

Ombudsman (local and/or state)

Closure Coordinator

_____  Create meeting agenda (see sample)

_____  Develop a plan to address residents who disrupt the meeting to the extent it has a negative impact on other residents and family members

_____  Invite nursing facility staff to attend the meeting for the purpose of supporting residents – staff who become disruptive must be removed from the meeting

_____  Limit entry to the meeting to families, residents, guardians, nursing facility staff and local closure team members – do not allow media into the meeting

Resident & Family Meeting Agenda

(when preparing copies for meeting, remove details in red)

1. Welcome and Introductions					Facility Administrator

2. Ground rules for meeting					Facility Administrator

3. Decision for closure						Facility Administrator

4. Introduce local closure team members and their roles	Facility Administrator

A representative from each agency will briefly discuss their role in the closure (see notes below)

Lead Placement Worker (facility SW) – discuss Person-Centered Discharge Planning process

Closure Coordinator – facilitate best practice protocol and serve as resource – Review Guide for Family/Guardian During Relocation and Facility Availability list and discuss DPNA and BOA

DHS - identify potential relocation settings and assist with placement - discuss how Medicaid follows the resident to new setting and how DHS can assist with guardianship or Medicaid eligibility issues

CMH – identify potential relocation settings and assist with placement for current clients

MIChoice Waiver – assist with placement for lesser level of care services – discuss what services are currently available

Ombudsman – advocate for residents and conduct support group meetings –review resident rights, Tips for Visiting handout, and process to be added to waiting list

Centers for Independent Living – review services available through organization

5. Daily routines, care and services				Facility Administrator

6. Discuss projected timeframe for closure			Facility Administrator

7. Assistance for employees					Facility Administrator

8. Questions and Answers

9.  Time for residents and families to meet with Placement Workers individually

Materials for Meeting

Tool kit for resident/family/guardian

Pens or Pencils for residents/family/guardian

Local Closure Team members may have additional materials to distribute

Information to Gather for Local Closure Team

The nursing facility administrator should assign staff to gather the following information.  Once gathered, this information will be given to the closure coordinator for distribution to local team members. Some information will be verbally reported during the local closure team meetings.

_____  Current resident roster with room numbers

_____  Face sheet with current guardianship information for each resident

_____  List of key facility personnel with contact information (within facility & for emergency)

_____  Identify for each resident (if not correct or contained on resident face sheet)

Legal guardian’s (court appointed) name, address, phone number

DPOA – name, address, phone number

Next of Kin – name, address, phone number

Active CMH Services – service provider name, address, phone number

Payment source status – private pay, third party insurance, Medicaid, Medicare

Physician, dental, optical and podiatry service provider

_____  Identify residents who

Could benefit from a lesser level of care (AFC, HFA, AL, Home, Apartment)

Need legal guardianship

Have pending Medicaid

Have no open Medicaid, but are eligible for services

Have upcoming appointments with doctors, dentist, optician, etc.

Have glasses, dentures, orthotic or medical devices on order

Need updated PASARR Level I or II

Have personal wheelchair, walker, geri chair, bed, etc to transfer

Are at risk for elopement or physical harm/abuse to self or others

_____ Print computer copies of resident face sheet & most recent MDS for discharge transfer packets

2004 Agency List For Access To Nursing Homes

These people/organizations are approved by Bureau of Health Systems to have access to nursing facility residents.

Judy Cerano, Interim Director, Association for Retarded Citizens-Michigan (ARC)

1325 S. Washington, Lansing, MI  48910

Suzanne Colley, CEO, Cass County Council on Aging, Inc.

60525 Decatur Road, P.O. Box 5, Cassopolis, MI  49031

Lois Hitchcock, Director/CEO, City of Southfield Commission of Sr. Adults

26000 Evergreen, Southfield, MI  48076

Nida Donar, ED, Citizens for Better Care

4750 Woodward Ave., #410, Detroit, MI  48201

George Martin, ED, Community Advocates for Persons with Developmental Disabilities

814 S. Westnedge, Kalamazoo, MI  49008-1162

Katherine White, ED, Elder Law of Michigan, Inc.

221 North Pine St., Lansing, MI  48933

Ward F. McDonough, Jr., CEO, Legal Aid Bureau of SW MI, Inc.

201 W. Kalamazoo Ave., Room 308, Kalamazoo, MI  49007

William R. Knight, Exec. Director, Lakeshore Legal Services, Inc.

21885 Dunham Road, Suite 4, Clinton Twp., MI  48036

Deierdre Weir, CEO, Legal Aid & Defender Assoc. & Senior Citizens Legal Aid Project

645 Griswold, Suite 2500, Detroit, MI  48226

Edward J. Hoort, CEO, Legal Services of Eastern Michigan

436 S. Saginaw Street, Flint, MI  48502

Elmer L. Cerano , Director, MI Protection & Advocacy Service

4095 Legacy Parkway, Suite 500, Lansing, MI  48911

Sheilah P. Clay, Director & CEO, Neighborhood Services Organization

220 Bagley, Suite 1200, Detroit, MI  48226

Dawn Jacobs, contact for John Swise, Director/CEO

Northeast Michigan Community Service Agency (NEMCSA)

2375 Gordon Road, Alpena, MI  49707

Darlene Eshenaur, R.N., President, Resident Advocates

1491 Ariebill SW, Wyoming, MI  49509

James F. Kelly, President/CEO, United Cerebral Palsy Association

23077 Greenfield, Suite 205, Southfield, MI  48075

Valaria Conerly, Exec. Director, Valley Area Agency on Aging

711 N. Saginaw, Suite 207, Flint, MI  48503

Michael Chielens, Western Michigan Legal Services

# 89 Ionia Avenue NW, Suite 400, Grand Rapids, MI  49503

# Equipment and Supply List for Closure

Equipment

# Operating Fax Machines (at least 2 for relocation process)

Extra cartridges and paper

# Computer & Printer for tracking relocation process

Extra cartridges and paper

Copiers for reproducing discharge transfer packets (at least three operating copiers)

Extra cartridges and paper

Two-way radios for use during discharges

Supplies

Discharge Transfer Packets

Large envelopes (at least 9 x 12)

Shipping labels (Avery 5164 or comparable brand)

- transfer packet label (one for name and one for checklist)

Packing Supplies

Boxes – medium size works well

Packing tape

Scissors or tape guns

Large markers

Shipping labels (Avery 5164 or comparable brand)

- for resident boxes/belongings (one sheet per resident)

Miscellaneous

Clipboards for placement workers

Desktop supplies

4” Binder to store resident placement forms

Accordion folders for organizing forms

Desktop trays for In & Out (for fax requests and scheduling transfers)

Plastic name badge holders and badges for residents (avoid using pin style)

Emergency Equipment

Flashlights and batteries

Emergency radio

Cell phones

Land-line telephone

Resident Belongings Delivery Form

(reformat for facility letterhead)

Residence

Delivery Date

By signing below, I accept receipt of the following resident belongings

Resident Name		Item/s Delivered

1.

2.

3.

4.

5.

# Signature of Receiver

# Title

Date

Agency Contact List

(This sample list is for Ingham County.  A facility specific list will be created for each closure event.  Specific contact names are added once the team members are identified.)

Michigan Department of Community Health

Medical Services Administration (Medicaid)

Long term Care Services Section

Mary Gear, Manager						517 335-5827

Salli Pung, Nursing Facility Closure Coordinator		Contact at nursing facility

Reimbursement and Rate Setting Section

John Donaldson, Manager						517 335-5363

Bureau of Health Systems

Division of Nursing Home Monitoring

Cora Urquhart, Licensing Officer					517 334-8421

Tom Gorney, Survey Monitor					517 334-8427

Ombudsman

Sarah Slocum, State Long Term Care Ombudsman		866-458-9393

Kristina Schmidgall, Local Ombudsman

Central Michigan Citizens for Better Care Office		800 292-7852

4700 Ardmore Ave, #102-A, Okemos, MI 48805		517 347-7398

Family Independence Agency

Ingham County Office						517 887-9400

5303 S. Cedar Street, Lansing, MI 48911			517 887-9500 (fax)

Area Agency on Aging

Tri-County Office on Aging 					800 405-9141

5303 South Cedar Street, Lansing, MI 48911-3800		517 887-1440

Community Mental Health

Clinton-Eaton-Ingham CMH Services Program			517 346-8200

812 East Jolly Rd, Suite 215-A, Lansing, MI 48910

Michelle Townsend, MSW, OBRA Coordinator			517 346-8439

Center for Independent Living

Capital Area Center for Independent Living			517 241-0393

Ellen Weaver, Executive Director

Closing Nursing Facility

Administrator

Director of Nursing

Lead Placement Worker

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Closure Coordinator Role and Responsibilities

The Closure Coordinator represents the State Closure Team as the lead worker on the local closure team, as a resource to the nursing facility staff, and as the main communication link between the local closure team and the state closure team.

The Closure Coordinator is responsible to:

- assess the nursing facility with the administrator to determine what additional resources may be needed

- mobilize and coordinate the state agency representatives on-site

- oversee the relocation of residents

- serve as a resource for conflict resolution

- assure that the relocation process is understood and followed by all parties

- assist the nursing facility administrator to identify nursing facility staff to serve in key closure roles, e.g., placement worker, scheduler, after-hours receptionist

- monitor adequacy of equipment and supplies needed during the relocation process

- report to the State Closure Team Leader on a daily basis

- offer guidance and task support to local closure team members and nursing facility staff as needed

- schedule a debriefing meeting with local closure team members

Closure Coordinator

Guide During Nursing Home Closure

_____  Meet with nursing facility administration and key nursing facility staff

_____  Designate work area for local closure team and secure office for equipment

_____  Complete nursing facility needs assessment with NF administrator

_____  Request resident face sheets and roster from NF administrator

_____  Coordinate notification of resident and family meetings with NF administrator

_____ Schedule on-site local closure team meeting with key NF staff and notify participants

_____	 Prepare meeting materials

_____	 Agenda

_____ Resident Placement Form (sample)

_____ Person-Centered Discharge Planning Form (sample)

_____ Level of Care Placement Worksheet (sample)

_____ Placement worker fax coversheet (sample)

_____ Overview of Relocation Options

_____ Information to gather at local closure team meeting

_____  Name, organization and phone number for each local closure team member

_____  Assignment of placement workers

_____  Post signs for local closure team work room

_____  Prepare work room with poster sized rosters

_____  Develop resident relocation roster

_____  Create resident specific forms (delegate to nursing facility staff if possible)

_____  Resident Placement Form

_____  Resident Relocation Tracking Form

_____  Person-Centered Discharge Planning Form

_____  Resident Belongings Packing List

_____  Packing Labels (one sheet for each resident - Avery 5160)

_____  Discharge Transfer Packet label (two labels – resident name and checklist)

_____  Name badge for each resident (use clip style holders – not pins)

_____  Create name badges for local closure team members

_____  Create Nursing Facility & Local Closure Team roster

_____  Prepare materials for Resident /Family Meeting (facility staff to reproduce packets)

_____  Resident/Family Guardian tool kit

_____  Facility list with bed availability, DPNA and BOA

_____  Resident Roster with placement worker assignments

Closure Coordinator

Guide During Nursing Home Closure Continued

_____  Display signs with information about the Resident and Family meetings at entrances and in common areas

_____  Contact MiWorks! if requested by administrator

_____  Report to State Closure Team Leader daily

_____  Serve as resource to local closure team members and nursing facility staff

_____  Collect post closure contact information from Administrator and key staff

_____  Distribute Facility Follow-up Post Closure checklist to Administrator and key staff

_____  Schedule post closure discussion meeting with local closure team members

_____  Distribute resident relocation roster to appropriate agencies post closure

Nursing Facility Needs Assessment Checklist

Staffing  & Placement Workers

Food Service

Vendors

Physical Plant

Security

Media

Other – request for MIWorks! to conduct on-site information meeting for staff?

Agenda for Local Closure Team Meeting

with Key Nursing Facility Staff

_____  Introductions (distribute sign-in sheet)

_____  Identify role of key nursing facility staff in relocation process

Notification (calls to families and meetings with residents)

Placement Workers (clinical staff to complete discharge planning process)

Scheduler (scheduling transfers, packing belongings, transferring)

Information Exchange (faxing requests, visitors, questions, receptionist)

_____  Review local closure team members’ roles & responsibilities

_____  Discuss lines of authority

Operations – Nursing Facility Administrator

Resident placement - DHS has oversight

Relocation process – Closure Coordinator

Regulatory issues - Licensing Officer

Media – line of authority varies – clarify at meeting

_____  Discuss conflict resolution process

_____  Discuss process and tools developed for information exchange

_____  Tour physical plant or give overview of layout (NF Administrator)

_____  Suggest appropriate parking area (NF Administrator)

_____  Review features of nursing facility  (NF Administrator)

Operation of phone system

Door alarms & required codes

Elevator codes

Evacuation protocol (share written copy)

Emergency exits

Restrooms

Smoking area/policy

_____  Schedule future daily meetings

_____  Allow for questions and answers

Nursing Facility Resource Phone Roster

Name						Phone (extension)		Emergency Number

________________, Administrator

________________, DON

________________, Social Worker

________________, Business Office

________________, Maintenance

________________,  ____________

Resident Council President

Family Council President

Pool Agency

Ambulance

Pharmacy

Foodservice

Other Vendors

Union Stewards

Local Union Office

Resident Relocation Tracking Form

Resident Name

Residence  								Phone

Address  								Fax

Contact

Transfer Date  				Time  		    	Confirmed with

Transfer type		Ambulance        Receiving Facility Vehicle	    Volunteer        Family/Guardian

Transfer packet sent with resident 					YES		    NO

Belongings sent at time of transfer (inventory sheet attached)	YES		    NO

Belongings remaining in facility

Medications  		sent with resident  			          returned to pharmacy

Resident Trust Fund disbursed   $  		          Check/MO#  		  Date

Patient Pay Amounts disbursed  $    	      	          Check/MO#  		  Date

Change of Address Card completed	             YES			 Date mailed

Social Security Check

Follow-up on resident status

Date				Person Contacted  					Initials

How is resident eating and sleeping

Are there any unexpected behaviors

Is the resident refusing care or medications

Is the resident participating in activities

Is the resident voicing any distress or concerns related to the move?

Did the resident’s belonging arrive safely

Do you need more information to care for the resident

Has the resident’s family/guardian completed the admission process

Comments

Local Closure Team Roster

| Agency | Name | Title/Position | Phone | Email |
| --- | --- | --- | --- | --- |
| MSA | Salli Pung | Closure Coordinator | 517 335-7225 | pungs@michigan.gov |
| MSA | Howard Schaefer | Policy Analyst | 517 241-0820 | SchaeferH1@michigan.gov |

Nursing Facility Staff Roster

| Name | Title/Position | Phone Extension | Assignment/Task |
| --- | --- | --- | --- |
|  | Administrator |  |  |
|  | Director of Nursing |  |  |
|  | Social Worker |  |  |
|  | Medical Records |  |  |
|  | MDS Nurse |  |  |
|  | Business Office Manager |  |  |
|  | Receptionist |  |  |
|  | Activity Director |  |  |
|  | Dietary Supervisor |  |  |
|  | Housekeeping Supervisor |  |  |

Receiving Residence Roster

| Residence (name & city) | Type of residence | Representative Name | Title/Position | Phone Number | Beds Available | Specialties |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Medicaid | Medicare | License Only | Specialized units or services |
|  |  |  |  |  | M | F | M | F | M | F |  |

Task/Team Assignments

| Task to be Completed | Lead | Team Members |
| --- | --- | --- |
| Call families & guardians to inform of closure and resident/family meeting |  |  |
| Inform residents of closure |  |  |
| Identify vacancies at nearby residences |  |  |
| Coordinate faxing of resident information to potential residence |  |  |
| Prepare for resident/family meeting (room set-up, signs, refreshments) |  |  |
| Pack and label resident belongings once scheduled for transfer |  |  |
| Copy medical records for transfer packets |  |  |
| Prepare resident medication & treatment records for transfer |  |  |
| Receiving residence coordinator – greet receiving residence visitors and direct to Local Team work room |  |  |
| Transportation coordinator – greet transportation driver and confirm resident for transfer |  |  |
| Disburse resident trust fund with current accounting for each resident |  |  |
| Disburse any patient pay or private pay balances |  |  |
| Complete change of address cards for residents |  |  |
| Notify receiving residence of any upcoming resident appointments or ordered appliances (dentures, glasses, orthotics, etc) and arrange for delivery |  |  |

Facility Follow-Up Post Closure

| Task to be Completed | Staff Assigned to Task | Date Completed |
| --- | --- | --- |
| Prepare remaining resident belongings and deliver to residents |  |  |
| Submit in writing to the L.O. and Closure Coordinator the location of and process to access residents’ medical records |  |  |
| Complete electronic discharge of residents in the MDS system |  |  |
| Post a sign at the entrances and update the message on answering machine to inform callers/visitors of contact name and number if they have questions or need additional information |  |  |
| Contact family/guardians to remove any large items from the facility, if necessary |  |  |

SAMPLE **Nursing Facility Name – Resident Relocation Roster ** SAMPLE

Updated:  10/19/04

| Rm # | Resident’s Name | Placement Worker | Guardian/Family name and relationship | Guardian Family Phone # | Date Guardian Contacted | Name of New Residence | Scheduled Transfer | wants staff help to pack | Time Resident Left Facility | Date Completed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Last | First |  |  |  |  |  | Date | Time |  |  | MDS | Clinical Record | Follow-up call |
| 102 | Brown | Anna | J. Smith DHS | Judy Brown Daughter, DPOA | 999 555-6789 | 10/03/04 | ABC Nursing Home | 10/15 | AM 9:00 | Yes | 10:00a | 10/16/04 | 10/16/04 | 10/18/04 |
| 106 | Jackson | Robert | L. Jones CMH | Own guardian - no family contact |  | 10/02/04 |  |  |  | Yes |  |  |  |  |
| 210 | Smith | Larry | L. Jones CMH | ABC Guardian Legal guardian | 999 555-7777 | 10/3/04 | Sunny Acres AFC | 10/20 | AM10:00 | No |  |  |  |  |
| 212 | Jones | Bernice | M. Frank Waiver | Harry Jones Husband, guardian | 999 555-1234 | 10/2/04 | Home with family | 10/10 | PM 2:00 | No | 1:00p | 10/10/04 | 10/11/04 | 10/12/04 |

Agency Contact List

(This sample list is for Ingham County.  A facility specific list will be created for each closure event.  Specific contact names are added once the team members are identified.)

Michigan Department of Community Health

Medical Services Administration (Medicaid)

Long term Care Services Section

Mary Gear, Manager						517 335-5827

Salli Pung, Nursing Facility Closure Coordinator		Contact at nursing facility

Reimbursement and Rate Setting Section

John Donaldson, Manager						517 335-5363

Bureau of Health Systems

Division of Nursing Home Monitoring

Cora Urquhart, Licensing Officer					517 334-8421

Tom Gorney, Survey Monitor					517 334-8427

Ombudsman

Sarah Slocum, State Long Term Care Ombudsman		866-458-9393

Kristina Schmidgall, Local Ombudsman

Central Michigan Citizens for Better Care Office		800 292-7852

4700 Ardmore Ave, #102-A, Okemos, MI 48805		517 347-7398

Family Independence Agency

Ingham County Office						517 887-9400

5303 S. Cedar Street, Lansing, MI 48911			517 887-9500 (fax)

Area Agency on Aging

Tri-County Office on Aging 					800 405-9141

5303 South Cedar Street, Lansing, MI 48911-3800		517 887-1440

Community Mental Health

Clinton-Eaton-Ingham CMH Services Program			517 346-8200

812 East Jolly Rd, Suite 215-A, Lansing, MI 48910

Michelle Townsend, MSW, OBRA Coordinator			517 346-8439

Center for Independent Living

Capital Area Center for Independent Living			517 241-0393

Ellen Weaver, Executive Director

Closing Nursing Facility

Administrator

Director of Nursing

Lead Placement Worker

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Director of Nursing Role and Responsibilities

The director of nursing (DON) must assure that care and services continue to be delivered in a manner that meets federal and state requirements.  The DON should work closely with the nursing facility staff scheduler to plan for staff call-ins and/or resignations and develop a plan to address staffing issues in advance.  The DON must demonstrate strong leadership during the nursing facility closure and show support for staff through out the process.  The DON has a major impact on staff performance and nursing facility morale.

The director of nursing is responsible to:

- monitor the delivery of care and services to assure residents’ needs are being met

- encourage staff to keep their morale up and to stay resident-focused

- insure that clinical records are accurate and up to date

- oversee accurate reproduction of resident discharge transfer packets

- assist in identifying residents who are candidates for lesser level of care

- reassign nursing staff as needed to assist in relocation tasks

Director of Nursing Guide During Nursing Facility Closure

_____  Participate in local closure team meetings

_____  Assure adequate staffing on all shifts

_____  Monitor care and service delivery

_____  Assure clinical records are accurate and complete

_____  Assign nursing staff to complete sections of the Person-Centered Discharge Planning form

Staff Insight Into Resident’s Quality of Life

Behavioral/Emotional (when applicable)

Screen for Independent Living (when applicable)

Functional Assessment

_____  Assign staff to produce discharge transfer packets (DON to monitor progress)

_____  Assign staff to complete Discharge Transfer Forms

_____  Assign staff to electronically discharge residents in the MDS system

_____  Report any concerns to the Administrator

Person-Centered Discharge Planning Form

Resident Name  						Room Number

Placement Worker 						Resident Gender:  Male   or    Female

RESIDENT INTERVIEW (conducted by placement worker)

What type of setting would you like to live in? (return home, live with family, AFC, HFA, NF, etc)

What would be important to you in this new environment? (safety, freedom, visitors, privacy, etc)

What preferences do you have for your living arrangements? (preferred furniture, organized vs lived-in)

What makes you happy?

What do you enjoy doing?

What would you like to do that you don’t do now?

How do you like your day to go?  Describe your typical day

What specific preferences do you have for care delivery? (bath vs shower, meals/day, caregiver gender)

What is your lifestyle like? (morning vs night person, introvert vs extrovert, alone vs group activities)

Resident Name  						Room Number

RESIDENT INTERVIEW continued

What is your ethnic/cultural background?

Are cultural activities   □  Very important	  □ Somewhat important	□  Not important at all

Needs/Preferences

What is your past or current religious affiliation(s) or denominations?

Spiritual or religious activities are    □ Very important    □ Somewhat important    □ Not important at all

Needs/Preferences

Support System (family, friends, neighbors, religious or community members, staff)

Important Events (anniversaries, births, deaths)

Nicknames

Hobbies

Skills

Schooling (level completed, where)

Occupation (company, how long, retired)

Veteran (war time, branch of service)

Community Organizations

Family (spouse, children, grandchildren)

Pets

Special residents or staff

How would you like to be welcomed at your new residence? (flowers, special meal, visitors, be left

alone, announcement, attend activities, etc)

Person-Centered Discharge Planning Form

Resident Name  						Room Number

STAFF INSIGHT INTO RESIDENT’S QUALITY OF LIFE (completed by nursing facility staff)

What is the resident’s preferred daily routine? (waking time, social interactions, nighttime activity, etc)

What is comforting to the resident? (type of music, certain activities, food items, possessions, etc)

Does the resident have favorite special foods or treats? (supplied by family/staff, ethnic, etc.)

What environment supports are available for the resident? (likes to sit by the window, prefers room door shut, sleeps with the lights on, likes to sit near the nurses station, etc)

Person completing this section 						Date

Person-Centered Discharge Planning Form

Resident Name  						Room Number

RESIDENTS WITH BEHAVIORAL OR EMOTIONAL DIFFICULTIES

(completed by nursing facility staff)

PSYCHOSOCIAL TRIGGERS

What emotions or situations trigger the resident? (Stressors, excitement, sadness, depression, outbursts)

Specific times or days it occurs?

Effective Interventions?

Person completing this section 						Date

Person-Centered Discharge Planning Form

Resident Name  						Room Number

SCREEN FOR RESIDENTS REQUESTING PLACEMENT

IN AN INDEPENDENT OR RESIDENTIAL SETTING

(completed by nursing facility staff)

Bathing			□ Independent		□ Partial Assistance		□ Total Assistance

Hygiene			□ Independent		□ Partial Assistance		□ Total Assistance

Dressing			□ Independent		□ Partial Assistance		□ Total Assistance

Telephone Use		□ Independent		□ Partial Assistance		□ Total Assistance

Shopping			□ Independent		□ Partial Assistance		□ Total Assistance

Food Prep			□ Independent		□ Partial Assistance		□ Total Assistance

Housekeeping		□ Independent		□ Partial Assistance		□ Total Assistance

Laundry			□ Independent		□ Partial Assistance		□ Total Assistance

Transportation		□ Independent		□ Partial Assistance		□ Total Assistance

Finances			□ Independent		□ Partial Assistance		□ Total Assistance

Mobility			□ Independent		□ Partial Assistance		□ Total Assistance

Eating			□ Independent		□ Partial Assistance		□ Total Assistance

Continence			□ Independent		□ Partial Assistance		□ Total Assistance

Comments:

Person completing this section 						Date

Person-Centered Discharge Planning Form

Resident Name  						Room Number

FUNCTIONAL ASSESSMENT (completed by facility Nursing staff)

Check if applicable

- Dependent for feeding

- Incontinence   	Bowel _____      	Bladder _____

- Dependent for bathing

- Dependent for dressing

- Tube feeding

- Elopement Risk    Explain

- IV Therapy

- Infection: Acute	    or   Chronic  			Type

- Needs Oxygen

- Pressure Ulcer(s) Location/Stage

- Dependent Transfer      x1_____     x2_____   Mechanical Lift _____

- Wheelchair for Mobility

- Communication Aids  (interpreter, communication board, sign language, hearing aid, etc)

- Special Needs or Equipment

Upcoming appointment (doctor’s name, purpose of visit or procedure, date, time, location, phone number)

Appliance on order (type, vendor, expected delivery date, contact name, phone number)

For relocation, how can the resident safely transfer?

- By ambulance (medically necessary)

- Wheelchair van with lift

- Motorized wheelchair

- Oversized wheelchair (check if it is:   wide ____   heavy _____   high____)

- Resident does not own wheelchair – transportation must supply one for transfer

- Car (ambulatory, can self-transfer and can safely ride in seat with seatbelt)

- Car (needs assistance transferring, but can safely ride in seat with seatbelt)

Person completing this section 						Date

Sample Discharge Transfer Packet Label

___   Guardianship Document           ____  Geri Chair

___   Advance Directive                     ____  Wheelchair

___   PASARR (3877 & 78)               ____  Walker

___  Nurses’ Notes (1 month)           ____  Cane

___   Physician’s Notes (1 month)     ____  TV

___   Physician’s Orders                    ____  Radio

___   Current Labs

___   Social Service Notes

___   Dietary Notes                        At Time of Transfer

___   Current Therapy Notes	___  Discharge Transfer Form

___   Psychiatric Notes 		___  Medical Admin Record

___   Activities Notes		___ Treatment Sheet

___   TB/Immunizations 		___  Resident ID

___   Podiatry Services		___  Belongings Packed

___   Dental Services			______  # of Boxes

___   Optical Services			______  # of Bags

___   Current Full MDS

___   Face Sheet

___   Current Chest X-Ray

Agency Contact List

(This sample list is for Ingham County.  A facility specific list will be created for each closure event.  Specific contact names are added once the team members are identified.)

Michigan Department of Community Health

Medical Services Administration (Medicaid)

Long term Care Services Section

Mary Gear, Manager						517 335-5827

Salli Pung, Nursing Facility Closure Coordinator		Contact at nursing facility

Reimbursement and Rate Setting Section

John Donaldson, Manager						517 335-5363

Bureau of Health Systems

Division of Nursing Home Monitoring

Cora Urquhart, Licensing Officer					517 334-8421

Tom Gorney, Survey Monitor					517 334-8427

Ombudsman

Sarah Slocum, State Long Term Care Ombudsman		866-458-9393

Kristina Schmidgall, Local Ombudsman

Central Michigan Citizens for Better Care Office		800 292-7852

4700 Ardmore Ave, #102-A, Okemos, MI 48805		517 347-7398

Family Independence Agency

Ingham County Office						517 887-9400

5303 S. Cedar Street, Lansing, MI 48911			517 887-9500 (fax)

Area Agency on Aging

Tri-County Office on Aging 					800 405-9141

5303 South Cedar Street, Lansing, MI 48911-3800		517 887-1440

Community Mental Health

Clinton-Eaton-Ingham CMH Services Program			517 346-8200

812 East Jolly Rd, Suite 215-A, Lansing, MI 48910

Michelle Townsend, MSW, OBRA Coordinator			517 346-8439

Center for Independent Living

Capital Area Center for Independent Living			517 241-0393

Ellen Weaver, Executive Director

Closing Nursing Facility

Administrator

Director of Nursing

Lead Placement Worker

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Scheduler Role and Responsibilities

With one designated scheduler, the nursing facility can assure a timely transfer for all residents. The scheduler is responsible to:

- coordinate transfer times to minimize traffic congestion at the facility entrance

- consider the resident’s preferred transfer time and resident’s routine when scheduling transfers

- communicate scheduled transfers to placement workers and nursing facility staff on a daily basis

- assure appropriate type of transportation is provided for each resident

- limit the number of residents going to any one location on a single day to 3 per location

- limit the total number of residents leaving the building on a single day to 10 per day

Scheduler Guide During Nursing Facility Closure

Scheduling Transfers

_____  Develop an IN and OUT box system for exchange of forms

_____  Receive Resident Placement Form from placement worker

_____  Confirm required mode of transportation (see Discharge Planning form)

_____  Contact admission coordinator at relocation setting

_____  Confirm acceptance of resident with new residence

_____  Determine date & time of transfer

_____  Confirm necessary mode of transportation

* Limit the number of residents transferring per day to any location to 2 or 3

* Limit the total number of residents leaving the facility per day to 10

_____  Record contact person’s name, and date & time of call on Resident Placement Form

_____  Fax Receiving Residence Tool Kit to new residence (when first resident is scheduled at that new residence)

_____  Update Resident Relocation Roster with name of new setting, transfer date and time

_____ Prepare Relocation Information Card

_____  Return Resident Placement Form and Relocation Information Card to placement worker

_____ Distribute updated Resident Relocation Roster on a daily basis to placement workers, facility staff, and local closure team members

Note:  Often potential residences will assume the resident is transferring to their location when a family member or resident visits or when information is sent over the fax.  It is important to only discharge residents scheduled for transfer.  In the event transportation shows up for a resident not on the schedule, the resident’s placement worker or the Closure Coordinator should be notified immediately to help confirm the placement and resolve the issue.  The exception to this rule is if a family member or guardian wants to transfer a resident without following this process.  The family may not know that support is available and assume the responsibility for placement and relocation.  In this event, it is best to support the transfer, although not pre-scheduled.

Sample Relocation Information Card

Resident’s Name: John Smith

ABC Nursing Home

125 E. Main Street

Anywhere, MI, 48999

Phone: 555 555-5555

Contact Person:  Ms. White, Admissions

Transfer Date:  Tuesday, April 26, 2005

Transfer Time:  9:30 am

SAMPLE ** Nursing Facility Name – Resident Relocation Roster ** SAMPLE

Updated:  10/19/04

| Rm # | Resident’s Name | Placement Worker | Guardian/Family name and relationship | Guardian Family Phone # | Date Guardian Contacted | Name of New Residence | Scheduled Transfer | wants staff help to pack | Time Resident Left Facility | Date Completed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Last | First |  |  |  |  |  | Date | Time |  |  | MDS | Clinical Record | Follow-up call |
| 102 | Brown | Anna | J. Smith DHS | Judy Brown Daughter, DPOA | 999 555-6789 | 10/03/04 | ABC Nursing Home | 10/15 | AM 9:00 | Yes | 10:00a | 10/16/04 | 10/16/04 | 10/18/04 |
| 106 | Jackson | Robert | L. Jones CMH | Own guardian - no family contact |  | 10/02/04 |  |  |  | Yes |  |  |  |  |
| 210 | Smith | Larry | L. Jones CMH | ABC Guardian Legal guardian | 999 555-7777 | 10/3/04 | Sunny Acres AFC | 10/20 | AM10:00 | No |  |  |  |  |
| 212 | Jones | Bernice | M. Frank Waiver | Harry Jones Husband, guardian | 999 555-1234 | 10/2/04 | Home with family | 10/10 | PM 2:00 | No | 1:00p | 10/10/04 | 10/11/04 | 10/12/04 |

Agency Contact List

(This sample list is for Ingham County.  A facility specific list will be created for each closure event.  Specific contact names are added once the team members are identified.)

Michigan Department of Community Health

Medical Services Administration (Medicaid)

Long term Care Services Section

Mary Gear, Manager						517 335-5827

Salli Pung, Nursing Facility Closure Coordinator		Contact at nursing facility

Reimbursement and Rate Setting Section

John Donaldson, Manager						517 335-5363

Bureau of Health Systems

Division of Nursing Home Monitoring

Cora Urquhart, Licensing Officer					517 334-8421

Tom Gorney, Survey Monitor					517 334-8427

Ombudsman

Sarah Slocum, State Long Term Care Ombudsman		866-458-9393

Kristina Schmidgall, Local Ombudsman

Central Michigan Citizens for Better Care Office		800 292-7852

4700 Ardmore Ave, #102-A, Okemos, MI 48805		517 347-7398

Family Independence Agency

Ingham County Office						517 887-9400

5303 S. Cedar Street, Lansing, MI 48911			517 887-9500 (fax)

Area Agency on Aging

Tri-County Office on Aging 					800 405-9141

5303 South Cedar Street, Lansing, MI 48911-3800		517 887-1440

Community Mental Health

Clinton-Eaton-Ingham CMH Services Program			517 346-8200

812 East Jolly Rd, Suite 215-A, Lansing, MI 48910

Michelle Townsend, MSW, OBRA Coordinator			517 346-8439

Center for Independent Living

Capital Area Center for Independent Living			517 241-0393

Ellen Weaver, Executive Director

Closing Nursing Facility

Administrator

Director of Nursing

Lead Placement Worker

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Nursing Facility Direct Caregivers Role and Responsibilities

Direct caregivers have the greatest impact on residents during the relocation process. CNAs, in addition to maintaining their daily routines, have the responsibility to:

- monitor for and report changes in the resident’s mental, emotional or clinical status during the closure process

- participate in discharge planning by conveying  the special needs and preferences of  residents to enhance continuity of care when the resident relocates to the new residence.

- facilitate a positive experience for residents by staying focused on the resident, being positive about the process, and offering support to the resident

- assist residents in packing belongings and transferring to the new residence

Nursing Facility Direct Caregivers

Guide During Nursing Facility Closure

Direct care workers have the greatest impact on residents during a nursing facility closure.  It is important for staff to stay focused on the resident’s needs and continue to provide the highest possible quality of care, while addressing resident’s concerns about relocation.  Let the resident determine the amount of assistance with packing, grooming, dressing, etc in preparation for transfer.

_____  Support residents emotionally throughout the process

_____  Monitor residents for changes in mental, emotional or medical state

_____  Report any change in resident’s condition to supervisor and placement worker

_____  Prepare the resident for the physical transfer

Night before transfer

_____ Assist the resident in packing and inventorying personal belongings

Assure all items are properly labeled

Retain at least one set of clothing for transfer day

Keep belongings in resident’s room until transfer

Clean television or other equipment/furniture

Apply label to back of equipment – not on TV screen

Label & tape remote to equipment

Complete inventory list to include in relocation packet and retain a copy for the nursing facility’s record

_____ Shower or bathe the resident, style hair, groom nails, etc

_____ Afternoon and midnight staff should encourage 1:1 time with the resident as this is the resident’s last night in the facility

Day of Transfer

_____ Assist the resident with grooming including oral care

_____	Assist the resident to dress in a clean set of clothing for transfer

Bag dirty clothing and label as such for transportation

_____	Escort resident to 1st floor entrance when vehicle arrives

_____	Load belongings into vehicle before resident

_____	Escort resident to vehicle

Allow adequate time for staff and residents to say good-bye

Resident Belongings Packing List

Resident Name  	            Room number

New Residence  						Transfer

Date		Time

Belts								Skirt

Bible								Slippers

Blouse								Slip

Boots								Socks

Books / Magazine						Suit

Bra								Suspenders

Coat / Jacket							Sweater

Denture: Upper / Lower					Sweat Pants

Dress								Sweat Shirt

Eye Glasses							Ted Hose

Eye Glass Case						TV /remote taped to TV		Hat / Cap							Undershirt

Nightgown							Underwear

Pajamas							Vest

Pants / Slacks							Walker / Cane

Personal Chair (recliner / Geri)				Wall Decoration

Personal Papers						Wallet

Purse								Wheelchair

Quilt / Comforter

Radio								Bag of Personal Items ***

Robe

Shaver (Electric)

Shirt

Shoes

Shorts

*** Could include perfume, make up, hair accessories, brush, comb, cards, photos, pencils, pens, address books, jewelry, etc.

On-site nursing facility staff should confirm no personal resident belongings are locked in the front office, nurses’ station, nursing facility storage areas, or medication carts.

Agency Contact List

(This sample list is for Ingham County.  A facility specific list will be created for each closure event.  Specific contact names are added once the team members are identified.)

Michigan Department of Community Health

Medical Services Administration (Medicaid)

Long term Care Services Section

Mary Gear, Manager						517 335-5827

Salli Pung, Nursing Facility Closure Coordinator		Contact at nursing facility

Reimbursement and Rate Setting Section

John Donaldson, Manager						517 335-5363

Bureau of Health Systems

Division of Nursing Home Monitoring

Cora Urquhart, Licensing Officer					517 334-8421

Tom Gorney, Survey Monitor					517 334-8427

Ombudsman

Sarah Slocum, State Long Term Care Ombudsman		866-458-9393

Kristina Schmidgall, Local Ombudsman

Central Michigan Citizens for Better Care Office		800 292-7852

4700 Ardmore Ave, #102-A, Okemos, MI 48805		517 347-7398

Family Independence Agency

Ingham County Office						517 887-9400

5303 S. Cedar Street, Lansing, MI 48911			517 887-9500 (fax)

Area Agency on Aging

Tri-County Office on Aging 					800 405-9141

5303 South Cedar Street, Lansing, MI 48911-3800		517 887-1440

Community Mental Health

Clinton-Eaton-Ingham CMH Services Program			517 346-8200

812 East Jolly Rd, Suite 215-A, Lansing, MI 48910

Michelle Townsend, MSW, OBRA Coordinator			517 346-8439

Center for Independent Living

Capital Area Center for Independent Living			517 241-0393

Ellen Weaver, Executive Director

Closing Nursing Facility

Administrator

Director of Nursing

Lead Placement Worker

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Other Nursing Facility Staff Role and Responsibilities

Activities staff have the responsibility to:

- offer increased meaningful activities during the relocation process

- utilize volunteers to increase resident social supports, especially for residents with dementia

- identify skills, strengths and preferences of residents to enhance the Person-Centered Discharge Planning process

Nursing staff, department managers and business office staff have the responsibility to:

- support the relocation process by serving in newly assigned roles

- complete specific resident relocation tasks as assigned

- insure care and services meet regulatory requirements

- participate in the Person-Centered Discharge Planning process

- report any concerns or resident needs to the facility administrator

- share special needs and preferences of residents with the placement workers to enhance discharge planning and continuity of care at the new residence

Other Nursing Facility Staff Guide During Nursing Facility Closure

NF Activities Staff

_____ Share insights into resident’s quality of life in this section of the Person-Centered Discharge Planning form

_____ Increase meaningful activities during nursing facility closure

_____ Schedule additional volunteers for group and 1:1 activities

NF Business Office

_____  Share insights into resident’s quality of life in this section of the Person-Centered Discharge Planning form

_____  Fax resident information to potential residences

_____  Route incoming calls appropriately

_____  Direct visitors to placement worker or local closure team work room

_____  Prepare an accounting of the resident’s trust fund and disburse any balance at the time of transfer

_____  Prorate PPA if necessary and forward any payment to receiving location

_____  Complete change of address cards and mail to the local Post Office

Other NF Staff as Assigned by NF Administrator

_____  Share insights into resident’s quality of life in this section of the Person-Centered Discharge Planning form

_____ Identify resident’s belongings in storage or laundry

_____ Insure all resident’s items are clearly marked with his/her name

_____	Assist the resident to inventory belongings

_____ Assist the resident to pack belongings and clearly label boxes

_____	Transfer resident’s belongings to transfer vehicle

_____	Support resident during the process

NF Nursing Staff

_____ Complete sections of the Person-Centered Discharge Planning Form

Staff Insight Into Resident’s Quality of Life

Behavioral/Emotional (when applicable)

Screen for Independent Living (when applicable)

Functional Assessment

_____ Discharge resident in MDS system

_____	Complete the discharge transfer form

_____ Coordinate medication administration with scheduled transfer time

_____	Copy Medication Administration Record and Treatment Administration Record just prior to the resident transferring to include in discharge transfer packet

_____	Hand-deliver discharge transfer packet to transportation driver

_____	Support resident during the process

Person-Centered Discharge Planning Form

Resident Name  						Room Number

Placement Worker 						Resident Gender:  Male   or    Female

RESIDENT INTERVIEW (conducted by placement worker)

What type of setting would you like to live in? (return home, live with family, AFC, HFA, NF, etc)

What would be important to you in this new environment? (safety, freedom, visitors, privacy, etc)

What preferences do you have for your living arrangements? (preferred furniture, organized vs lived-in)

What makes you happy?

What do you enjoy doing?

What would you like to do that you don’t do now?

How do you like your day to go?  Describe your typical day

What specific preferences do you have for care delivery? (bath vs shower, meals/day, caregiver gender)

What is your lifestyle like? (morning vs night person, introvert vs extrovert, alone vs group activities)

Resident Name  						Room Number

RESIDENT INTERVIEW continued

What is your ethnic/cultural background?

Are cultural activities   □  Very important	  □ Somewhat important	□  Not important at all

Needs/Preferences

What is your past or current religious affiliation(s) or denominations?

Spiritual or religious activities are    □ Very important    □ Somewhat important    □ Not important at all

Needs/Preferences

Support System (family, friends, neighbors, religious or community members, staff)

Important Events (anniversaries, births, deaths)

Nicknames

Hobbies

Skills

Schooling (level completed, where)

Occupation (company, how long, retired)

Veteran (war time, branch of service)

Community Organizations

Family (spouse, children, grandchildren)

Pets

Special residents or staff

How would you like to be welcomed at your new residence? (flowers, special meal, visitors, be left

alone, announcement, attend activities, etc)

Person-Centered Discharge Planning Form

Resident Name  						Room Number

STAFF INSIGHT INTO RESIDENT’S QUALITY OF LIFE (completed by nursing facility staff)

What is the resident’s preferred daily routine? (waking time, social interactions, nighttime activity, etc)

What is comforting to the resident? (type of music, certain activities, food items, possessions, etc)

Does the resident have favorite special foods or treats? (supplied by family/staff, ethnic, etc.)

What environment supports are available for the resident? (likes to sit by the window, prefers room door shut, sleeps with the lights on, likes to sit near the nurses station, etc)

Person completing this section 						Date

Person-Centered Discharge Planning Form

Resident Name  						Room Number

RESIDENTS WITH BEHAVIORAL OR EMOTIONAL DIFFICULTIES

(completed by nursing facility staff)

PSYCHOSOCIAL TRIGGERS

What emotions or situations trigger the resident? (Stressors, excitement, sadness, depression, outbursts)

Specific times or days it occurs?

Effective Interventions?

Person completing this section 						Date

Person-Centered Discharge Planning Form

Resident Name  						Room Number

SCREEN FOR RESIDENTS REQUESTING PLACEMENT

IN AN INDEPENDENT OR RESIDENTIAL SETTING

(completed by nursing facility staff)

Bathing			□ Independent		□ Partial Assistance		□ Total Assistance

Hygiene			□ Independent		□ Partial Assistance		□ Total Assistance

Dressing			□ Independent		□ Partial Assistance		□ Total Assistance

Telephone Use		□ Independent		□ Partial Assistance		□ Total Assistance

Shopping			□ Independent		□ Partial Assistance		□ Total Assistance

Food Prep			□ Independent		□ Partial Assistance		□ Total Assistance

Housekeeping		□ Independent		□ Partial Assistance		□ Total Assistance

Laundry			□ Independent		□ Partial Assistance		□ Total Assistance

Transportation		□ Independent		□ Partial Assistance		□ Total Assistance

Finances			□ Independent		□ Partial Assistance		□ Total Assistance

Mobility			□ Independent		□ Partial Assistance		□ Total Assistance

Eating			□ Independent		□ Partial Assistance		□ Total Assistance

Continence			□ Independent		□ Partial Assistance		□ Total Assistance

Comments:

Person completing this section 						Date

Person-Centered Discharge Planning Form

Resident Name  						Room Number

FUNCTIONAL ASSESSMENT (completed by facility Nursing staff)

Check if applicable

- Dependent for feeding

- Incontinence   	Bowel _____      	Bladder _____

- Dependent for bathing

- Dependent for dressing

- Tube feeding

- Elopement Risk    Explain

- IV Therapy

- Infection: Acute	    or   Chronic  			Type

- Needs Oxygen

- Pressure Ulcer(s) Location/Stage

- Dependent Transfer      x1_____     x2_____   Mechanical Lift _____

- Wheelchair for Mobility

- Communication Aids  (interpreter, communication board, sign language, hearing aid, etc)

- Special Needs or Equipment

Upcoming appointment (doctor’s name, purpose of visit or procedure, date, time, location, phone number)

Appliance on order (type, vendor, expected delivery date, contact name, phone number)

For relocation, how can the resident safely transfer?

- By ambulance (medically necessary)

- Wheelchair van with lift

- Motorized wheelchair

- Oversized wheelchair (check if it is:   wide ____   heavy _____   high____)

- Resident does not own wheelchair – transportation must supply one for transfer

- Car (ambulatory, can self-transfer and can safely ride in seat with seatbelt)

- Car (needs assistance transferring, but can safely ride in seat with seatbelt)

Person completing this section 						Date

Resident Belongings Packing List

Resident Name  	            Room number

New Residence  						Transfer

Date		Time

Belts								Skirt

Bible								Slippers

Blouse								Slip

Boots								Socks

Books / Magazine						Suit

Bra								Suspenders

Coat / Jacket							Sweater

Denture: Upper / Lower					Sweat Pants

Dress								Sweat Shirt

Eye Glasses							Ted Hose

Eye Glass Case						TV /remote taped to TV		Hat / Cap							Undershirt

Nightgown							Underwear

Pajamas							Vest

Pants / Slacks							Walker / Cane

Personal Chair (recliner / Geri)				Wall Decoration

Personal Papers						Wallet

Purse								Wheelchair

Quilt / Comforter

Radio								Bag of Personal Items ***

Robe

Shaver (Electric)

Shirt

Shoes

Shorts

*** Could include perfume, make up, hair accessories, brush, comb, cards, photos, pencils, pens, address books, jewelry, etc.

On-site nursing facility staff should confirm no personal resident belongings are locked in the front office, nurses’ station, nursing facility storage areas, or medication carts.

Agency Contact List

(This sample list is for Ingham County.  A facility specific list will be created for each closure event.  Specific contact names are added once the team members are identified.)

Michigan Department of Community Health

Medical Services Administration (Medicaid)

Long term Care Services Section

Mary Gear, Manager						517 335-5827

Salli Pung, Nursing Facility Closure Coordinator		Contact at nursing facility

Reimbursement and Rate Setting Section

John Donaldson, Manager						517 335-5363

Bureau of Health Systems

Division of Nursing Home Monitoring

Cora Urquhart, Licensing Officer					517 334-8421

Tom Gorney, Survey Monitor					517 334-8427

Ombudsman

Sarah Slocum, State Long Term Care Ombudsman		866-458-9393

Kristina Schmidgall, Local Ombudsman

Central Michigan Citizens for Better Care Office		800 292-7852

4700 Ardmore Ave, #102-A, Okemos, MI 48805		517 347-7398

Family Independence Agency

Ingham County Office						517 887-9400

5303 S. Cedar Street, Lansing, MI 48911			517 887-9500 (fax)

Area Agency on Aging

Tri-County Office on Aging 					800 405-9141

5303 South Cedar Street, Lansing, MI 48911-3800		517 887-1440

Community Mental Health

Clinton-Eaton-Ingham CMH Services Program			517 346-8200

812 East Jolly Rd, Suite 215-A, Lansing, MI 48910

Michelle Townsend, MSW, OBRA Coordinator			517 346-8439

Center for Independent Living

Capital Area Center for Independent Living			517 241-0393

Ellen Weaver, Executive Director

Closing Nursing Facility

Administrator

Director of Nursing

Lead Placement Worker

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Receiving Residence Role and Responsibilities

The receiving residence has the responsibility to thoroughly review the needs of potential residents for admission and appropriately plan for the resident’s arrival to insure continuity of care and quality of life as defined by the resident.

The receiving location is responsible to:

- thoroughly review the resident’s medical needs and living preferences

- support visits by interested residents and family members

- accurately represent available care and services

- support the physical relocation of the resident

- transport the resident’s belongings

- prepare for the resident’s arrival in accord with the resident’s needs and preferences

- monitor the resident during the first 2-3 days after transfer for unexpected outcomes

Receiving Residence Guide

During Nursing Facility Closure

The receiving residence can have a significant impact on the resident’s transition.  By reviewing and planning ahead of time for the resident’s needs and preferences as described on the Person-Centered Discharge Planning form, the new residence is able to provide a warm, sensitive welcome tailored to the resident.  This guide was created for transfer to other long term care residences, but many of the suggestions are applicable for the resident returning home or moving in with family, as well as community residences.

_____  Share availability/occupancy information with local closure team members when contacted

_____  Support on-site visits by residents and families

_____  Arrange for a tour – show visitor the actual room if possible

_____  Consider having the visitor join in a meal or activity

_____  Identify staff and residents to interact with the visitor – consider need for private conversations without the admissions staff

_____  Share written materials with the visitor including contact name and number

_____  Offer a follow-up visit if the visitor is interested

_____  Prompt visitor for questions or concerns

_____  Review resident information faxed to you (face sheet, discharge plan, physician orders)

_____ Thoroughly review resident’s needs and preferences when considering acceptance

_____ If more information is needed, arrange an on-site visit with the resident

_____ For a Medicaid resident relocating to another Nursing Facility, the MiChoice Waiver or PACE programs in a voluntary closure, complete the LOC Eligibility tool upon admission

_____  Contact the placement worker as soon as a decision regarding acceptance is made

_____  If at full occupancy, offer to add resident to the waiting list

_____  Work with the closing nursing facility’s scheduler to determine the best transfer date and time for the resident

_____  Schedule transportation for the resident and his/her belongings

_____  Offer to accompany the resident during the transfer

Receiving Residence Guide

During Nursing Facility Closure Continued

Prepare for the resident’s arrival

_____  Prepare the resident’s room – be sure resident’s name is posted near the door

_____  Consider how to welcome the resident

_____  Create a “buddy” system with other residents, volunteers or staff

_____  Contact the family to discuss the resident’s transition needs and any concerns

_____	 Confirm arrival time with family/guardian and request their presence at arrival

_____  Inform staff and residents of new resident’s planned arrival time

_____  Inform resident and family council presidents of new resident/family

_____  Plan a special activity for the new resident – see discharge planning for ideas on comfort items or familiar activities

_____  Determine how to support a resident with dementia in the new residence

_____  Identify an individual to serve 1:1 as a greeter and guide for the first few days at the resident’s request

Upon resident’s arrival

_____ Introduce the new resident to “buddy”, caregivers and roommates

_____ Council presidents should welcome resident and family

_____ Ask the resident what would make them comfortable in the new surroundings

_____ Orient resident to the lifestyle of the facility (facility tour, meal schedule, services)

_____ Offer resident support in unpacking belongings and arranging personal items

_____ Connect resident with other residents transferred from closing nursing facility

_____ Distribute materials in transfer packet so staff on all shifts are knowledgeable of resident’s care needs and preferences for activities and daily routine

_____ Establish resident trust fund

_____ Contact the local social security office to change resident’s address on social security check, if necessary

_____ For a resident with dementia, consider balancing the amount of interaction and assessment on the first few days with the resident’s specific needs (too much interaction may cause greater confusion for the resident in a new surrounding)

_____ Contact placement worker with any questions or concerns

_____ Monitor resident closely for the first two or three days

_____ Watch for signs of depression, stress, unexpected disorientation or elopement attempts

_____  Determine interventions to better support resident’s transition

_____ Share transition observations of resident during follow-up calls or on-site visits by DHS, Ombudsman, and Nursing Facility Closure Coordinator

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Licensing Officer and Survey Monitor Role and Responsibilities

The Licensing Officer and Survey Monitor role is to insure that residents’ health and safety are protected and that the facility remains compliant with state and federal regulations through the closure.

The survey agency staff are responsible to:

- serve as a source of information and advice during the closure process

- schedule surveyors to monitor the facility regularly during closure

- monitor care and services deliver during closure

- discuss licensure with the nursing facility administration

- notify the federal government (CMS) of the nursing facility closure

Licensing Officer and Survey Monitor

Guide During Nursing Facility Closure

_____ Offer guidance to nursing facility administrator

_____ Notify the Director of the Division of Nursing Home Monitoring of nursing facility’s decision to close

_____ Review current enforcement status with Enforcement Unit in BHS/Div of Operations

_____ Schedule survey staff to monitor the nursing facility

_____ Consider participating in the resident and family meetings

_____ Discuss concerns of on-site surveyor visits with nursing facility administrator

_____  Inform Closure Coordinator of surveyor concerns, if additional assistance is required

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

MSA LTC Services Section Manager

Role and Responsibilities

The Medical Services Administration oversees the relocation of residents during a nursing facility closure through the appointment of the Nursing Facility Closure Coordinator.  The MSA Long Term Care Services Section Manager serves as the State Nursing Facility Closure Team leader and oversees the work of the Closure Coordinator.

The MSA LTCS Section Manager is responsible to:

- advise the facility during the decision process

- activate the on-site services of the Closure Coordinator

- notify the following of the nursing facility closure

      - State Closure Team members

      - MSA Administration

      - MSA Reimbursement and Rate Setting

      - MSA Provider Eligibility

- coordinate notification of DCH media office with BHS

- monitor the nursing facility closure process

MSA LTC Services Section Manager

Guide During Nursing Facility Closure

_____  Notify the following of nursing facility closure

_____  State Closure Team Members

_____  MSA Administration

_____  MSA Reimbursement and Rate Setting

_____  MSA Provider Eligibility

_____  Closure Coordinator

_____  Coordinate notification of closure to DCH media office with BHS

_____  Review current enforcement status of nursing facility with BHS-Div of Operations

_____  Review financial standing of facility and identify areas of concern

_____  Schedule Closure Coordinator’s arrival at nursing facility

_____  Request DPNA/BOA list from BHS-Division of Operations

_____  Request facility ranking list by compliance history from BHS-Div of Operations

_____  Identify MSA staff to participate in resident and family meetings, if needed

_____  Schedule daily reporting with Closure Coordinator

_____  Report progress of closure to State Nursing Facility Closure Team as needed

_____  Notify when closure is complete

_____  State Closure Team Members

_____  MSA Administration

_____  MSA Reimbursement and Rate Setting

_____  MSA Provider Eligibility

BHS Licensing Officer

BHS Division of Operations, Data Management Unit

Forward final resident relocation roster to

_____  MSA Reimbursement and Rate Setting

_____  State LTC Ombudsman

_____  State DHS office

_____  Local DHS office

_____  Coordinate post closure discussion with BHS staff and the nursing facility administrator

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Department of Human Services Role and Responsibilities

Local DHS Adult Services staff have the responsibility to oversee the relocation process for residents during a nursing facility closure.  DHS staff may be asked by the nursing facility or Closure Coordinator to serve as placement workers.

Local DHS Adult Services supervisors are responsible to:

- schedule staff

- arrange for on-site equipment including wireless phones

- coordinate with DHS Eligibility Specialist Workers to:

    - facilitate resident address and level of care changes for Medicaid recipients

    - determine current Medicaid status for residents

    - assist with new and pending Medicaid applications

Local DHS Adult Services staff are responsible to:

- determine bed availability/vacancies for local nursing facilities, home for aged and adult foster care facilities

- assist in locating and notifying families and guardians of the closure when requested by the nursing facility

- serve as placement workers upon request

- attend the resident and family meeting to distribute information, answer questions and offer support to residents and family members

DHS Adult Services Staff Guide During Nursing Facility Closure

DHS Adult Services Supervisor

_____ Identify lead DHS worker to coordinate services with Closure Coordinator

_____ Facilitate Medicaid status clearances on all residents once face sheets are received from Closure Coordinator

_____ Schedule staff to serve as placement workers at the nursing facility if requested

_____ Identify staff to participate in meetings at the nursing facility

_____  Lead DHS worker at the initial Local Closure Team and Key NF Staff meeting

_____  DHS staff serving as placement workers at the daily local team meetings

_____  DHS Adult Services workers at the resident and family meetings

_____ Arrange for equipment to use at nursing facility (desk top supplies, cell phones, etc)

DHS Adult Services workers

_____ Determine bed availability at local nursing, home for aged, and adult foster care facilities

_____ Notify residents, families and guardians of closures as requested by the nursing facility

_____ Attend the resident and family meeting(s) to distribute information, answer questions and offer support to residents and family members

_____ Serve as placement workers as requested by the nursing facility and/or closure coordinator

_____ Lead worker and adult service workers (serving as placement workers) participate in daily local team meetings

_____ Lead worker forwards daily updates on placement to local office for processing

**  DHS staff serving as placement workers will utilize the Placement Worker tool kit for the resident relocation process.

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Local Community Mental Health Service Provider

Role and Responsibilities

The local community mental health service provider (CMHSP) insures appropriate placement for residents receiving mental health services.  The CMHSP may be asked by the nursing facility to serve as placement workers for the residents receiving mental health services.

The local CMHSP is responsible to:

- oversee the placement for all residents receiving mental health services through their agency

- serve as placement worker for current clients to insure informed choice and continuity of care

- assist with counseling for residents and staff having difficulty with the closure

- assess other residents identified during the closure process who may need mental health services

- complete Level II PASARR assessments as needed

- conduct follow-up visits with the resident in his or her new residence

Local Community Mental Health Service Provider

Guide During Nursing Facility Closure

_____ identify lead CMH worker to coordinate services with the Closure Coordinator

_____ identify residents receiving mental health services at the closing nursing facility

_____ serve as placement worker for current clients in closing nursing facility**

_____ participate in local closure team meeting

_____  complete Level II PASARR assessments as needed

_____ counsel residents receiving mental health services during relocation process

_____ support other residents identified as needing mental health services

_____ discuss resident needs with placement workers

_____ serve as placement workers if requested

_____ participate in the resident and family meetings

**  Local CMH staff serving as placement workers will utilize the Placement Worker tool kit for the resident relocation process.

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

MIChoice Waiver Agent Role and Responsibilities

The local MIChoice Waiver agent is responsible for accepting referrals for residents interested in the MIChoice Waiver program.

The Waiver Agents will be responsible to:

- educate residents and families about program service options

- respond in a timely manner to referrals for waiver services

- assess residents referred to the program for placement possibilities

- coordinate service delivery with resident discharge plan

MIChoice Waiver Agent

Guide During Nursing Facility Closure

_____ respond to request for local assistance

_____ determine availability of program services

_____ participate in local closure team meeting

_____ complete an assessment for residents interested in services under the MIChoice Waiver program

_____ collaborate with the placement worker during the discharge planning process

_____ discuss concerns or barriers with the placement worker

_____ schedule services to coordinate with resident discharge to insure no gap in services

_____  if community transition cannot be completed within the nursing facility closure timeframe, continue community transition efforts after resident’s discharge to the temporary residence

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Long Term Care Ombudsman Role and Responsibilities

Local and State Long Term Care Ombudsman’s role during a nursing facility closure is to advocate for resident rights and informed choice.

Local and state ombudsman representatives have the responsibility to:

- support residents during the relocation process

- insure that resident’s rights are protected

- report potential violations of regulatory requirements to the Licensing Officer

- offer relocation information and assistance to residents and families

- coordinate and facilitate support group meetings for residents and families during the closure process

- advise residents of their rights during a closure

- help assist families interpret quality of care information about placement options

- assist placement workers as they help families with discharge planning

Long Term Care Ombudsman

Guide During Nursing Facility Closure

_____ Respond to request for increased monitoring

_____ Prepare educational materials regarding resident rights for residents, families and guardians

_____ Attend the local closure team and key nursing facility staff meeting

_____ Participate in the resident and family meetings

_____ Coordinate and facilitate support group meetings for residents and families

_____  Share information about local residences with residents and families

_____ Communicate residents’ needs and concerns with placement workers

_____ Support resident during the relocation process

_____ Advocate for resident rights and informed choice

_____ Share concerns with the Closure Coordinator

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Center for Independent Living Role and Responsibilities

The local Center for Independent Living (CIL) representative’s role is assist in the placement and transition of a resident wishing to relocate to a community setting.

The CIL representatives will be responsible to:

- educate interested residents and families about community service options

- respond in a timely manner to referrals for potential clients

- coordinate service delivery with resident discharge plan

Center for Independent Living

Guide During Nursing Facility Closure

_____ participate in local closure team meeting if possible

_____ determine availability of community transition options

_____ discuss and review community transition options with interested residents and families

_____ complete an assessment for residents interested in community transition

_____ initiate CIL transition protocol

_____ collaborate with the placement worker during the Person-Centered Discharge Planning process

_____ discuss concerns or barriers with the placement worker

_____ schedule services to coordinate with resident discharge to insure no gap in services

_____  if community transition cannot be completed within the nursing facility closure timeframe, continue community transition efforts after resident’s discharge to the temporary residence

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

Hospice Service Provider Role and Responsibilities

The local Hospice service provider’s role is to continue palliative care and end of life support services to current clients and their families during the relocation process.

The Hospice provider will be responsible to:

- educate residents and families about relocation options

- respond in a timely manner to referrals for Hospice services

- support the resident and family emotionally during the relocation

- coordinate Hospice services with resident’s discharge

- function as placement worker for clients currently being served by Hospice

Hospice Service Provider

Guide During Nursing Facility Closure

_____ support the resident and family during the relocation

_____ participate in local closure team meeting, if possible

_____ collaborate with or serve as the placement worker during the discharge planning process

_____ discuss placement concerns or barriers with local team members

_____ schedule services to coordinate with resident discharge to insure no gap in services

Overview of Relocation Options

|  | Type | Description of Services | Age | Payment Source | Eligibility Requirement | Contact |
| --- | --- | --- | --- | --- | --- | --- |
| Nursing Facility | Nursing facility (NF, CMCF, HLTCU) | A residential facility providing housing, meals, nursing and rehabilitative care, medical services and protective supervision for post-acute and long-term needs. | --- | Medicaid Medicare Private Pay | Physician order stating the need for continuous nursing care | Individual facility |
| Residential Services | Home for Aged | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 60 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Adult Foster Care | A living situation where room, board, personal care, protection, and supervision is provided, but not intense medical supervision. | 18 years or older | Medicaid/ SSI Private Pay | Varies among each facility | DHS – Adult Services |
|  | Assisted Living | Non-licensed residences offering room and board and limited care and supervision. | --- | Private Pay | Varies among each facility | Mi Assisted Living Assoc |
| Home and Community-Based Services | Home Health | Skilled nursing care is provided by a licensed nurse, or by a skilled rehabilitation therapist for speech, occupational or physical therapy. Personal care may be provided by home health aides. | --- | Medicaid Medicare Private Pay | The person must meet medical criteria and have a physician’s order | Physician or Home Health Agency |
|  | Physical Disability Services (PDS) | Provides assistance purchasing durable medical equipment and home modifications not otherwise covered by Medicaid. | 18 years or older | Medicaid | Persons must have a medical need | DHS – Adult Services |
|  | Home Help | Provides unskilled hands-on assistance with personal care such as help preparing meals, eating, grooming, and moving around the home. | --- | Medicaid | Persons must have a functional limitation in an ADL or IADL and need hands-on assistance | DHS – Adult Services |
|  | Mi Choice Program | Provides services and personal care that allow a person to remain in their home, including homemaker and chore services, home-delivered meals, adult day care, home modifications, specialized equipment or medical supplies, counseling and respite care. | 18 years or older | Medicaid | Person must meet nursing facility level of care criteria and require one of thirteen waiver services | Waiver Agent or local AAA |
|  | Program of All-Inclusive Care for the Elderly (PACE) | Provides all Medicare and Medicaid covered services in an adult day center model. The PACE program is only available in parts of Wayne County. | 55 years or older | Medicare and Medicaid | Person must meet nursing facility level of care criteria and live in the service area | PACE provider |
| Hospice | Hospice (provided at home, Nursing or hospice facility) | Hospice services include skilled care, personal care, palliative care, symptom and pain management, counseling and family support for people at the end of life and their families. | --- | Medicaid Medicare Private Pay | A physician order showing that the person is expected to die within six months | Local hospice agency |

Flowchart for Nursing Facility (NF) Closure Process

Long Term Care Acronym List

AAA 		Area Agency on Aging

ACP 		Adult Community Placement, Div. of OAS, MDHS

ADA 		Americans with Disabilities Act

ADL 		Activities of Daily Living

AFC		Adult Foster Care

AL		Assisted Living

ALOS		Average Length of Stay

AMA		Against Medical Advice

APS 		Adult Protective Services

BHS		Bureau of Health Systems, MDCH

BOA 		Ban on Admissions

CBC 		Citizens for Better Care

CCRC 		Continuing Care Retirement Community

CIL		Center for Independent Living

CMH 		Community Mental Health

CMP		Civil Monetary Penalty

CNA		Certified Nurse Aide or Assistant

CON		Certificate of Need

CSW 		Certified Social Worker

DCH		Department of Community Health

DD		Developmentally Disabled

DHS		Department of Human Services (formerly Family Independence Agency – FIA)

DHHS		Dept of Health and Human Services, Federal

DME		Durable Medical Equipment

DNR 		Do Not Resuscitate

DPNA		Denial of Payment for New Admissions

DPOA		Durable Power of Attorney

FIA		Family Independence Agency (currently Department of Human Services)

FOIA 		Freedom of Information Act

HCBS 		Home & Community Based (waiver) Services

HFA		Homes for the Aged

HHA		Home Health Agency

HHS		Home Help Services, Office of Adult Services, DHS

HIPAA		Health Insurance Portability and Accountability Act

HLTCU	Hospital Long Term Care Unit

HMO		Health Maintenance Organization

IADL 		Instrumental Activities of Daily Living

IJ		Immediate Jeopardy, enforcement

JCAHO 	Joint Commission on Accreditation of Healthcare Organizations

LO		Licensing Officer, Division of Nursing Home Monitoring

LOS 		Length of Stay

LPN		Licensed Practical Nurse

LSC		Life Safety Code

LTC		Long Term Care

MA		Medicaid

MC 		Medicare

MCF		Medical Care Facility

MDS 		Minimum Data Set (part of Resident Assessment Instrument)

MH		Mental Health

MIOSHA	MI Occupational & Safety Administration

MSA		Medical Services Administration, MDCH

NCCNHR 	National Citizens Coalition for Nursing Home Reform

NF		Nursing Facility

NH		Nursing Home

NHA		Nursing Home Administrator

NIA		National Institute on Aging

NP		Nurse Practitioner

OAS 		Office of Adult Services, DHS

OBRA 		Omnibus Budget Reconciliation Act

OSA		Office of Services to the Aging

OT		Occupational Therapy or Therapist

OTC		Over The Counter drugs

PACE 		Program of All-Inclusive Care for the Elderly

PASARR 	Pre-Admission Screening & Annual Resident Review

PNA		Personal Needs Allowance ($/month for aged, blind or disabled)

POC		Plan of Correction

PPA 		Patient-Pay Amount

PPD		Per Patient Day

PRN		Latin "pro re nata", as needed

PSDA 		Patient Self Determination Act

PT		Physical Therapy or Therapist

QA 		Quality Assurance

QI		Quality Indicators

RAI 		Resident Assessment Instrument

RAP		Resident Assessment Protocol

RD 		Registered Dietitian

RN		Registered Nurse

ROM		Range of Motion

SA		Survey Agency, Division of Nursing Home Monitoring

SDA		State Disability Assistance

SM		Survey Monitors, Division of Nursing Home Monitoring

SNF 		Skilled Nursing Facility

SOM		State Operations Manual, CMS

SQC		Substandard Quality of Care, enforcement

SSA		Social Security Administration

SSN		Social Security Number

SW		Social Worker

TLD 		Therapeutic Leave Days, nursing homes

VA 		Veterans Administration

Website Links and Other Resources

Internet Resources for Residents, Families and Guardians

Guide to Choosing a Nursing Home –http://www.medicare.gov/publications/pubs/pdf/nhguide.pdf

Medicaid Eligibility - http://www.cms.hhs.gov/medicaid/whoiseligible.asp#aged

Office of Services to the Aging - http://www.miseniors.net/MiSeniors+Home/

Michigan Long Term Care Portal - http://www.michigan.gov/ltc

Long Term Care Ombudsman

National Long Tem Care Ombudsman Center - http://www.ltcombudsman.org

Citizens for Better Care - http://www.cbcmi.org

Resources for Locating Settings and Services

Nursing Home Compare - http://www.medicare.gov/NHCompare/home.asp

Home Health Compare - http://www.medicare.gov/HHCompare/Home.asp

Veterans Facilities Locator - http://www1.va.gov/directory/guide/home.asp?isFlash=1

National and State Veteran Homes - http://www.vethomesfoundation.org

Michigan Statewide Search for Nursing Homes - http://www.cis.state.mi.us/bhs_car/sr_car.asp

Adult Foster Care (AFC) and Home for Aged (HFA) Locator - 					http://www.cis.state.mi.us/brs_afc/sr_afc.asp

Home Help – eligibility determined by DHS - http://www.michigan.gov/fia

MI Choice Waiver Program

http://www.michigan.gov/mdch/0,1607,7-132-2943_4857_5045-16263--,00.html

MI Choice Waiver Agents

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=8

Home Health Agencies - http://mhha.org

Hospice Providers - http://www.mihospice.org/find/vnl

Michigan State Housing Development Authority – Director of Subsidized Housing http://www.michigan.gov/mshda/0,1607,7-141--84992--,00.html

Michigan Disability Resource Directory - http://mdrd.state.mi.us/

Other Resources

Centers for Independent Living - http://www.cacil.org/directory.htm

Department of Human Services - http://www.michigan.gov/fia

United Way - http://www.uwmich.org

Local Public Transportation Agencies - http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=20

Local Councils and Commissions on Aging

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=13

Michigan Department of Civil Rights – Local offices

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=16

Senior Centers

http://www.miseniors.net/CMS_MiSeniors/search/agency2.asp?CatID=7&AgencyTypeID=14

Medicaid Help Line (bills or payments)

Phone: (800) 642-3195

Medicare/Medicaid Assistance Program

Phone: (800) 803-7174

Fraud & Abuse Complaint – Attorney General

Phone: (800) 242-2743

Legal Hotline for Michigan Seniors

Phone: (800) 347-5297

Nursing Home Complaint Intake Unit – State Survey Agency

Phone: (800) 882-6006

Behavioral Health Complaint Line – Specialized Mental Health Services

Phone: (800) 854-9090

Adult Foster Care and Home For Aged Complaint Intake Unit

Phone: (866) 856-01256

# Text boxes

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Complete Resident Follow-up

Discharge resident from facility

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

On-site visits by resident & family/guardian

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Person-centered Discharge planning process begins

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Discuss closure process and assign placement workers

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Nursing Facility Administrator and Closure Coordinator Meeting

- Discuss plan for closure

- Review nursing facility closure best practice process including roles and responsibilities

- Review administrator tool kit

- Identify facility personnel to serve as placement workers and scheduler

- Determine additional need for placement workers from local agencies including Department of Human Services, Community Mental Health, Centers for Independent Living, Area Agency on Aging, and Hospice

- Schedule date, time and location for resident and family meeting(s)

- Develop notification process for residents, families, and facility staff

Nursing Facility Management Staff Meeting with

Nursing Facility Administrator and Closure Coordinator

- Inform management staff of closure and reasons for decision

- Review nursing facility closure best practice process including roles and responsibilities

- Assign facility personnel to serve as placement workers

- Assign facility personnel to notify residents of closure and review process

- Assign facility personnel to notify families and guardians of closure (refer to letter for guidance)

Nursing Facility Staff meetings with

Nursing Facility Administrator and Closure Coordinator

- Inform NF staff of closure – hold one meeting per shift

- Discuss staff’s role in closure

- Utilize checklist in NF administrator tool kit for meeting

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Local Closure Team and Key Nursing Facility Staff Meeting

- Discuss progress from Day 1

- Review Person-Centered Discharge Planning process and tool kit

- Assign a placement worker to each resident

- Discuss process for faxing materials for placement

- Discuss process for notifying scheduler of placement

- Assign staff to prepare materials for resident and family meeting

- Assign staff to fax resident information to facilities

- Assign staff to serve as the scheduler and discuss process

- Assign staff to prepare the meeting room for the resident and family meetings and discuss room set-up

- Discuss concerns or issues

Resident

Information Faxed

Local Closure Team and Key Nursing Facility Staff Meeting

- Discuss progress from previous days

- Discuss Person-Centered Discharge Planning progress, barriers and concerns

- Review and update resident relocation roster

- Discuss process for assisting residents in packing and assuring all items are inventoried, packed, and appropriately labeled

- Discuss process for residents’ physical transfer out of the building

- Discuss process for resident and family meetings including participation by team members

- Discuss concerns or issues

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Resident and Family Meetings

- Discuss decision for closure

- Identify placement worker assignments

- Review resident/family/guardian tool kit

- Discuss resources available throughout the relocation process

- Discuss concerns or issues

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Relay transfer information to placement worker

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Prepare resident for transfer and pack belongings

Transfer resident and belongings to new residence

Complete Resident Follow-up

Discharge resident from facility

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Inform resident and family of transfer date and time

Yes

Resident accepted

No

Information reviewed for admission

Resident

Information Faxed

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Utilizing the Best Practices Tool Kit creates a protective barrier from stress and negative outcomes around the resident

Utilizing appropriate resources and following prescribed processes supports the resident

This approach keeps the resident at the center of the process while allowing the resident to drive the decision-making process.

Resident

Nursing facility staff

Placement workers

State and local agency staff

Informed choice

Coordination

Teamwork

Families

Negative outcomes

Person-centered discharge planning

Stress

Relay transfer information to placement worker

Discuss closure process and assign placement workers

Schedule date and time of transfer & update roster

Confirm transportation needs

Notify scheduler (submit relocation form)

Yes

No

Reconfirm location with Resident/ Guardian

Placement worker discusses preferences with resident for relocation & identifies potential residences

Prepare relocation materials

Resident and

Family Meetings

Notification to family/guardians by phone calls by NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to NF staff

Notification to State Agencies by NF Administrator

Decision to close nursing facility

Person-centered Discharge planning process begins

On-site visits by resident & family/guardian

Resident

Information Faxed

Information reviewed for admission

No

Resident accepted

Yes

Inform resident and family of transfer date and time

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Discharge resident from facility

Complete Resident Follow-up

Transfer resident and belongings to new residence

Prepare resident for transfer and pack belongings

Relay transfer information to placement worker

Discuss closure process and assign placement workers

Schedule date and time of transfer & update roster

Confirm transportation needs

Notify scheduler (submit relocation form)

Yes

No

Reconfirm location with Resident/ Guardian

Placement worker discusses preferences with resident for relocation & identifies potential residences

Prepare relocation materials

Resident and

Family Meetings

Notification to family/guardians by phone calls by NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to NF staff

Notification to State Agencies by NF Administrator

Decision to close nursing facility

Person-centered Discharge planning process begins

On-site visits by resident & family/guardian

Resident

Information Faxed

Information reviewed for admission

No

Resident accepted

Yes

Inform resident and family of transfer date and time

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Discharge resident from facility

Complete Resident Follow-up

Transfer resident and belongings to new residence

Prepare resident for transfer and pack belongings

Resident

Information Faxed

On-site visits by resident & family/guardian

Person-centered Discharge planning process begins

Decision to close nursing facility

Notification to State Agencies by NF Administrator

Notification to NF staff

Notification to Residents in 1:1 meetings with NF staff

Notification to family/guardians by phone calls by NF staff

Resident and

Family Meetings

Prepare relocation materials

Placement worker discusses preferences with resident for relocation & identifies potential residences

Reconfirm location with Resident/ Guardian

No

Yes

Notify scheduler (submit relocation form)

Confirm transportation needs

Schedule date and time of transfer & update roster

Discuss closure process and assign placement workers

Relay transfer information to placement worker

Information reviewed for admission

No

Resident accepted

Yes

Inform resident and family of transfer date and time

Disburse Resident Trust Fund and PPA balance

Complete  Change of Address Card

Discharge resident from facility

Complete Resident Follow-up

Transfer resident and belongings to new residence

Prepare resident for transfer and pack belongings

Local Closure Team and Key Nursing Facility Staff Meeting

- Discuss progress from previous days

- Discuss Person-Centered Discharge Planning progress, barriers and concerns

- Discuss challenging placements and identify solutions

- Review and update resident relocation roster

- Quick verbal update from each team member to discuss any concerns or issues